## Guidance
Equity Plan Reporting Template
Since the initial roll out for Equity Plans in school year 2018-19, TEA worked with representatives from ESCs to update and revise the reporting template for Texas school districts. Per federal guidelines (ESEA 1112(b)(2)), equity plans are required for all districts who receive Title I funds. This template should support a district's broader continuous improvement process to ensure that districts, and schools, identify gaps and take action to address differences in outcomes specifically for students who identify as African American, Hispanic, and/or low-income.
Guidance for Using the Equity Plan Template
This template is structured using the following required steps (see corresponding tabs below) to facilitate the development of the district's Equity Plan: If needed, districts may access exemplar Equity Plan Templates here.
Step 1: Review Current Data & Conduct a Root Cause Analysis (RCA)
Not Yet Started | Review and reflect on the current equity plan by using the guiding questions to see which strategies have been successful and have significantly eliminated the identified gaps.
Not Yet Started | Provide a problem statement that is aligned to the findings in the equity gap analysis of current district data and focuses on the challenge of attracting, supporting, or retaining effective teachers in the highest need campuses serving low-income and students of color
Not Yet Started | Provide root causes that are aligned to the problem statements as they relate to attracting, supporting, and retaining excellent teachers.
Not Yet Started | Engage with stakeholders in your district, including teachers, parents/guardians, and students, to gather their perceptions on the successes and challenges of the prior year’s equity plan to inform the development of this year’s equity plan. This feedback could be gathered during PTA meetings, staff meetings, or via surveys sent to stakeholder
Not Yet Started | Completed Step 1 tab.
Step 2: Select Strategies & Plan for Implementation
Not Yet Started | Select strategies that are directly aligned to the root cause analysis.
Not Yet Started | Continue implementing strategies that were on track from previous Equity Plan
Not Yet Started | Select strategies that are measurable, evidence-based, and aligned to the district commitments in Lever 1, 2, or 5 of the Effective Schools Framework.
Not Yet Started | Select benchmarks that are directly aligned to the selected strategies, viable within district’s specific context, and are measurable.
Not Yet Started | Consider strategies for stakeholder engagement & input to ensure buy-in for the process & outcomes.
Not Yet Started | Completed Step 2 tab.
Step 3: Monitor Progress & Fidelity of Implementation (FOI)
Not Yet Started | Conduct a detailed formative equity progress check multiple times throughout the year (at least BOY, MOY, & EOY) with the progress monitoring team.
Not Yet Started | Use or develop a progress tracking sheet that indicates the equity gap and the benchmarks that are directly aligned to each strategy (see OPTIONAL tabs below).
Not Yet Started | Communicate progress of the equity plan implementation to stakeholders to continue to keep them informed of the district’s commitment to achieving equity. This could include sharing updates in district and school newsletters, at school meetings and functions, and as an agenda item at PTA meetings
Not Yet Started | <Optional> Complete Action Plan & Progress Tracking Tool tab.
Not Yet Started | <Optional> Complete Monitor Progress & FOI tab.
Not Yet Started | Completed Step 3 tab.
Step 4: Submit Completed Equity Plan to TEA
Not Yet Started | Equity Plan Submitted via ISAM successfully by XXXX, 202X.

## Step 1 Review Data (Reqd)
Step 1. Review Current Data and Conduct a Root Cause Analysis
Reflection guidance for LEAs who have an existing Equity Plan For LEAs who do not have an existing Equity Plan, skip to the next section with root cause identification. | 1. Did the aligned strategy to eliminate the idenfied gap accomplish the desired equity goal according to the performance measure target? | 2. Will you continue implementing your existing strategy with enhancements or choose a new strategy for next year's equity plan? | 3. What lessons have you learned in the past two years and how will those lessons inform next year's equity plan?
| Our plan has helped in recruiting more qualified bilingual teachers, we no longer have a shortage of bilingual certified teachers in our highest percentage low-income campuses. Although it isn't included in our previous equity plan, we are currently pursuing funding from the Teacher Incentive Allotment as part of Cohort C with a start date of Spring 2022. | We are choosing two new strategies for next year's equity plan. We are going to shift our focus to developing our teacher capacity and effectiveness through professional development oppportunities. We are also planning on implementing a data driven process that will allow campus leaders to evaluate teacher effectiveness based on academic student growth data. | We have learned that often times our problems around recruiting and retaining teachers are out of our realm of control. We want to shift our focus to building campus leader capacity in developing systems to increase effective teachers on our campuses.
Using the rows below, capture any potential root causes that the data revealed. In the first row of each category, write the highest leverage root cause for the district to address. (Note: you may not have root causes in all four sections attract, assign, support, retain).
Root Causes as They Relate to ATTRACTING Effective Teachers | Root Causes as They Relate to ASSIGNING Effective Teachers | Root Causes as They Relate to SUPPORTING Effective Teachers | Root Causes as They Relate to RETAINING Effective Teachers
District does not have a mentoring or support program to support out of field teachers that have been reassigned | District has no system in place to place teachers strategically. | District has a high number of inexperienced teachers who are not appropriately prepared to serve African-American, Hispanic and Economically Disadvantaged students. | The retention rate for teachers is very low, with majority of teachers in their first 5 years.
District reputation and accountability ratings keep applicants from applying for positions. | Principals are not fully aware of their teachers strengths and weaknesses in relation to student growth.
Prioritization of Root Causes & Rationale
Based on the identification of root causes in the previous section, which category or categories (i.e. attracting, assigning, supporting, and/or retaining) are of the highest priority to address in your Equity Plan? These root causes will be the foundation for choosing strategies in Step 2.
Prioritized Category 1: | Supporting Effective Teachers
Rationale for Prioritized Category 1: Add a narrative for your team's rationale for prioritizing this first root cause | Our current teaching staff includes a large number of teachers with under five years experience. We are also staffed with several teachers going through the alternative teacher certfication program. Our professional development in the past has focused on curriculum, classroom management, and lesson planning. Our teachers are not provided with learning opportunities that allow them to be exposed to a variety of teaching strategies and differentiation techniques. We need to provide professional development that builds capacity in meeting the needs of a diverse student population through a varitey of researach based workshops.
Prioritized Category 2: | Assigning Effective Teachers
Rationale for Prioritized Category 2: Add a narrative for your team's rationale for prioritizing this second root cause | We do not currently have a system in place for analyzing, responding, and tracking student growth data. As a result, our campus leaders are not aware of teachers strengths and weaknesses in relation to student growth. We need to develop a system that creates a culture of data driven instruction that will allow our teachers to respond to students needs and campus leaders the information needed to make staffing/assignment decisions.
Based on your analysis, now draft your problem statement with a focus on the challenge of attracting, assigning, supporting, or retaining effective, experienced, and in-field teachers in the highest need campuses serving low-income, African-American, and Hispanic students. Provide at least one root cause that is aligned to the problem statement as it relates to attracting, supporting and retaining effective teachers. Be sure the root cause analysis (RCA) reflects district, campus, and teacher levels. (For more support with this task, see hyperlink in Row 11 of the GUIDANCE tab.)
Problem Statement: (The text you provide in the following cell will auto-populate on Step 3) | The district has a lack of professional development and implementation support for instructional practices which address the academic needs of African-American, Hispanic and Economically Disadvantaged students. Also, there is a lack of systemic data driven processes for leaders to assess and monitor teacher effectiveness in relation to student growth.

## Step 2 Plan for Impl. (Reqd)
Step 2. Select Strategies & Plan for Implementation
Problem Statement (From Step 1): | The district has a lack of professional development and implementation support for instructional practices which address the academic needs of African-American, Hispanic and Economically Disadvantaged students. Also, there is a lack of systemic data driven processes for leaders to assess and monitor teacher effectiveness in relation to student growth. |  |  |  | This section should include your high-level plan for your district. When you move to step 3, you'll plan implementation with more granularity for each (sub)strategy.
Root Cause Category (from Step 1) | Identified Root Cause (from Step 1) | Selected Equity Plan Strategies | ESF Lever | District Commitment | Year 1 Mid-Year Milestone(s) | Year 1 End-of-Year Milestone(s) | Year 2 Mid-Year Milestone(s) | Year 2 End-of-Year Milestone(s) | Optional Year 3 Mid-Year Milestone(s) | Optional Year 3 End-of-Year Milestone(s)
What highest leverage root cause(s) have you identified to address? | Enter the your identified root cause(s) for this category in Step 1. | What strategy will you implement locally to address the identified root cause problem? | Which ESF Lever most closely aligns to your identified root cause? | Based on the ESF Lever chosen in column D, you'll want to input the District Commitment that most closely aligns to your intended strategy
Root Causes as They Relate to SUPPORTING Effective Teachers | District has a high number of inexperienced teachers who are not appropriately prepared to serve African-American, Hispanic and Economically Disadvantaged students. | Provide professional development which focuses on the academic needs of African-American, Hispanic and Economically Disadvantaged students. | Lever 5 Effective Instruction | The district has effective systems for identifying and supporting struggling learners | By ________, identify and schedule professional development series for instructional best practices. | By ________, roll out professional learning series to 100% of new and veteran staff, and evaluate the PD to administrative staff. | By _________, provide and evaluate PD to new and new to district teachers throughout the academic school year. | Review & evaluate PD by ________. If not successful, then identify adjustments, make necessary refinements. | Continue to implement instructional best practices using the monitoring system and continue to adjust based on growth data. | Review and evaluate the effectiveness of instructional strategies through the use of formative and summative student growth data to determine the effectiveness of ongoing profressional development.
Root Causes as They Relate to ASSIGNING Effective Teachers | Principals are not fully aware of their teachers strengths and weaknesses in relation to student growth. | All instructional leadership staff will design and adopt a system for Data Driven Instructional processes to focus on teacher effectiveness in relation to student growth. | Lever 1 Strong School Leadership and Planning | The district provides opportunities for ongoing support and coaching of the campus leader. | By ________, contact ESC regarding Data Driven Instruction training options for the Summer. | By __________, 100% of identified campus and district leaders will be trained and prepared to rollout DDI systems for teacher effectiveness. | By _________, campus and district leaders will provide identified campus instructional staff with training in the DDI systems. | By __________, campus leaders will use the DDI system and process to evaluate student growth and determine teacher effectiveness, which will then inform teacher assignments for the following year. | By ___________ principal managers will observe the campus principal and evaluate feedback and coaching through the DDI process and make adjustments based on student growth data and teacher effectiveness. | Review and evaluate the effectiveness of principal coaching for the implementation of Data Driven systems of monitoring and feedback and tracking student growth data in relation to teacher effectiveness and assignments.

## Step 3 Progress Monitor (Reqd)
Step 3. Plan Progress Monitoring
Create a Sustainable Team & Structure: The district team, once created, will establish a time & place to collect and review evidence of progress toward each goal and strategy. There should also be meetings scheduled in advance to review data throughout the year to monitor progress. In addition to the table below, the Progress Monitoring Team may also consider using the OPTIONAL tabs for Monitoring Progress toward reaching the identified goals.
Proposed Equity Plan Progress Monitoring Team |  |  | Responsibilities (consider point-person(s) for tasks, deadlines, data management & analysis, and meeting preparation)
John Smith: Superintendent |  |  | Research and provide professional development opportunities for both campus leaders and instructional staff.
Patty Jones: Director of Instruction |  |  | Documentation and collection of data for each strategy. Monitoring implementation of new instructional strategies and data driven systems.
Sue Fuentes: Campus Principal |  |  | Implementation and monitoring at the campus level of proposed strategies. Assist with data collection.
Jerry Sims: Teacher |  |  | Implementation of proposed strategies. Support new or inexperienced teachers in the implementation.
Tiffany Black: Teacher |  |  | Implementation of proposed strategies. Support new or inexperienced teachers in the implementation.
Use the list of strategies and milestones from Step 2 Selecting Strategies to help you complete the blank Progress Monitoring Plan Template below. Each strategy that you have chosen should have its own progress monitoring plan; record them in the top left corner of the Progress Monitoring Plan Template. Some strategies may be complex; thus, it may be useful to break them into smaller sub-strategies. Your team should discuss each strategy in turn and make sure that the final progress monitoring plan has enough detail so that someone who is unfamiliar with your equity plan can understand how the strategy will be implemented in your district.
Problem Statement: | The district has a lack of professional development and implementation support for instructional practices which address the academic needs of African-American, Hispanic and Economically Disadvantaged students. Also, there is a lack of systemic data driven processes for leaders to assess and monitor teacher effectiveness in relation to student growth. |  |  |  | Long-Term Outcomes: (i.e. the changes your team expects to see in 2+ years) | Students from all of the sub-population groups will be performing at a high level and meeting all targets evaluated. There will not be a gap in performance between groups. Campus leaders will have the data needed to make informed decisions on staffing and assignments. Teacher capacity and effectiveness will be increased through targeted professional development opportunities.
Root Cause | Strategies & Substrategies | Year 1 Mid-Year Milestone(s) |  |  | Year 1 End-of-Year Milestone(s) |  | Year 2 Mid-Year Milestone(s) |  | Year 2 End-of-Year Milestone(s) |  | Optional Year 3 Mid Year Milestone(s) |  | Optional Year 3 End of Year Milestone(s)
What highest leverage root cause(s) have you identified to address? | What strategies and substrategies will you implement to address this root cause? | What are the next steps you will take to implement this strategy and achieve the outcome(s)? | If your strategy is well implemented, what will you see in up to 6 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 6–12 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 12–18 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 18–24 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 24-36 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 36-48 months? | What data will you collect to help you know if this strategy is working?
District has a high number of inexperienced teachers who are not appropriately prepared to serve African-American, Hispanic and Economically Disadvantaged students. | Provide professional development which focuses on the academic needs of African-American, Hispanic and Economically Disadvantaged students. | Complete the process to select a vendor with expertise in designing instuctional practices that address the needs of African-American, Hispanic and Economically Disadvantaged students. Develop a training schedule with selected vendor to support onsite training for school leaders and staff (ideally, school based teams made up of school leaders, teacher leaders, new and veteran teachers should attend the training series). | 100% of schools will be be able to identify specific ways in which the content from the professional learning has been implemented with fidelity in the daily rhythm of teaching and learning. | Formative assessment growth data, benchmark/interim assessment data, teacher observation data, teacher feedback survey data, student attendance data. | At least 80% of teachers will show engagement and growth in their effective execution of instructional practices by the end of the year. | Formative assessment growth data, benchmark/interim assessment data, teacher observation data, teacher feedback survey data, student attendance data. | At least 90% of teachers will show engagement and growth in their effective execution of instructional practices by the end of the year. Focus on induction and mentoring of new teachers and new to the district teachers to receive training on instructional practices with increased leadership support. | Formative assessment growth data, benchmark/interim assessment data, teacher observation data, teacher feedback survey data, student attendance data. | At least 100% of teachers will show engagement and growth in their effective execution of instructional practices by the end of the year. |  | At least 90% of teachers will show engagement and growth in their effective execution of instructional practices by the end of the year. Focus on induction and mentoring of new teachers and new to the district teachers to receive training on instructional practices with increased leadership support. | Formative assessment growth data, benchmark/interim assessment data, teacher observation data, teacher feedback survey data, student attendance data | At least 100% of teachers will show engagement and growth in their effective execution of instructional practices by the end of the year. | Formative assessment growth data, benchmark/interim assessment data, teacher observation data, teacher feedback survey data, student attendance data.
Principals are not fully aware of their teachers strengths and weaknesses in relation to student growth. | All instructional leadership staff will design and adopt a system for Data Driven Instructional processes to focus on teacher effectiveness in relation to student growth. | 100% of identified campus leaders will attend the DDI training provided by their local ESC. | Leaders will be developing an assessment calendar, meeting schedule, consistent protocols for data meetings, a tracker to monitor student growth and teacher effectiveness, and plan DDI PD for instructional staff. | Formative assessment growth data, benchmark/interim assessment data, DDI protocol documents, student/teacher data trackers, teacher observation data, teacher feedback survey data, student attendance data. | Campus leaders will be prepared to rollout DDI PD to instructional staff as evidenced by calendars, teacher/student trackers, DDI protocols and expectations as well as a PD plan. | Formative assessment growth data, benchmark/interim assessment data, DDI protocol documents, student/teacher data trackers, teacher observation data, teacher feedback survey data, student attendance data. | Campus leadership providing PD for instructional staff in data driven instruction. Beginning implementation of data meetings with campus leadership tracking student growth data and teacher effectiveness using student assessment data, reteach plans and re-assessment data. | Formative assessment growth data, benchmark/interim assessment data, DDI protocol documents, student/teacher data trackers, teacher reteach plans and re-assessment data, teacher observation data, teacher feedback survey data, student attendance data. | Campus leadership using the data driven instruction processs to monitor student growth and make adjustments in teacher assignments based on the data indicating the level of teacher effectiveness. |  | Principal managers evaluating the effectiveness of the campus data driven instruction process. Feedback and coaching conversations with the campus principal regarding levels of implementation. | Formative assessment growth data, benchmark/interim assessment data, DDI protocol documents, student/teacher data trackers, teacher reteach plans and re-assessment data, teacher observation data, teacher feedback survey data, student attendance data. | A decrease to below 10% gap between student groups and an increase in teacher effectiveness. The ability for campus leadership to make assignment decisions based on student data and teacher effectiveness. Continue the DDI system into subsequent years. | Formative assessment growth data, benchmark/interim assessment data, DDI protocol documents, student/teacher data trackers, teacher reteach plans and re-assessment data, teacher observation data, teacher feedback survey data, student attendance data.

## Action Plan & Progress Tracking
This tab is OPTIONAL and can be used for internal district planning and instructions as needed.
Equity Action Plan and Progress Tracking Tool (For each six month cycle, make a copy of this tab and edit as necessary.)
| Strategy #1 |  | Strategy #2 |  | Strategy #3 |  | Strategy #4 |  | Strategy #5 | Strategy #6
Selected Strategy
District Commitment
Annual Desired Milestone for Strategy
Desired Mid-Year Milestone
Barriers to address during this cycle
Action Plan-Milestones
Milestones | Year of Implementation | Selected Strategy | Timeline | Resources Needed | Person(s) Responsible | Metric/Evidence Used to Determine Progress Toward Milestone |  | Evidence Collection Date | Progress Toward Milestone | Necessary Adjustments/ Next Steps
Note on A2: This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on. ======

## Monitor Progress & FOI (OPTIONA
This tab is OPTIONAL and can be used for internal district planning and instructions as needed. This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on.
Monitor Progress and Fidelity of Implementation (For each six month cycle, make a copy of this tab and edit as necessary.)
Date Range: | Strategy and sub-strategy: |  |  | Type of outcome examined: |  | Mid-Year Y1 | End-of-Year Y1 | Mid-Year Y2 | End-of-Year Y2
Did our team do what was planned for this strategy? If not, what changes were made and why?
Did the data we collected help us to know if the strategy was implemented?
Describe any additional data we may need to help us understand this more or make better decisions.
To what extent have we made progress toward our goals? |  | Exceeded Goal(s) | Significant Progress |  | Some Progress |  | No Progress
Describe how we shared progress with stakeholders.
Do we need to make any adjustments at this time? If yes, please describe what changes we will make.
To what extent was the implementation of this strategy successful? Highlight the cell with your response and explain in row 19. |  | High level of success & fidelity of implementation |  | Some level of success and/or fidelity of implementation |  | No success and/or fidelity of implementation
If YES: How will we sustain this strategy? What factors need to be in place? If NO: Why wasn't the strategy implemented? What are the barriers to implementation? What are the next steps to ensure implementation or change the strategy? If it was implemented, but was only SOMEWHAT successful or did not lead to the expected outcome, was the strategy implemented with fidelity? What are next steps to take to improve outcomes?
Provide any additional insights we learned from completing this process or provide any additional information we think is necessary to understand our plan.
Note on A2: This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on. ======

## Data validation (hidden)
Lever | Lever_1_Strong_School_Leadership_and_Planning | Lever 2 Strategic Staffing | Lever 3 Positive School Culture | Lever 4 High-Quality Instructional Materials and Assessments | Lever 5 Effective Instruction
Lever 1 Strong School Leadership and Planning | 1.1. Develop campus instructional leaders with clear roles and responsibilities. | 2.1 Recruit, select, assign, induct, and retain a full staff of highly qualified educators | 3.1 Explicit school-wide behavioral expectations and culture routines | 4.1 Daily use of high-quality instructional materials | 5.1 Professional Development for Effective Classroom Instruction
Lever 2 Strategic Staffing | 1.2. Compelling and aligned vision, mission, goals, values focused ona safe environment, high expectations, and rigorous instruction. |  | 3.2 Proactive and responsive student support services |  | 5.2 Build teacher capacity through observation and feedback cycles
Lever 3 Positive School Culture | 1.3 Focused plan development and regular monitoring of implementation and outcomes |  | 3.3 Involving families and community |  | 5.3 Data-driven instruction
Lever 4 High-Quality Instructional Materials and Assessments | 1.4. The district provides the campus with adequate funding and sufficient control over their budget to ensure access to necessary resources for implementation of the school’s improvement plan and high-quality instruction to meet students’ learning needs. |  |  |  | 5.4 MTSS for students with learning gaps
Lever 5 Effective Instruction