## Guidance
The column titles for this worksheet are in rows 2, and 10. They span cells A2 through L2, and A10 through L10 . The data spans cells A3 through L33. There is information in every cell for columns A through L. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
Equity Plan Reporting Template
Since the initial roll out for Equity Plans in school year 2018-19, TEA worked with representatives from ESCs to update and revise the reporting template for Texas school districts. Per federal guidelines (ESEA 1112(b)(2)), equity plans are required for all districts who receive Title I funds. This template should support a district's broader continuous improvement process to ensure that districts, and schools, identify gaps and take action to address differences in outcomes specifically for students who identify as African American, Hispanic, and/or low-income.
Guidance for Using the Equity Plan Template
This template is structured using the following required steps (see corresponding tabs below) to facilitate the development of the district's Equity Plan
Step 1: Review Current Data & Conduct a Root Cause Analysis (RCA)
Not Yet Started | Review and reflect on the current equity plan by using the guiding questions to see which strategies have been successful and have significantly eliminated the identified gaps.
Not Yet Started | Provide a problem statement that is aligned to the findings in the equity gap analysis of current district data and focuses on the challenge of attracting, supporting, or retaining effective teachers in the highest need campuses serving low-income and students of color
Not Yet Started | Provide root causes that are aligned to the problem statements as they relate to attracting, supporting, and retaining excellent teachers.
Not Yet Started | Engage with stakeholders in your district, including teachers, parents/guardians, and students, to gather their perceptions on the successes and challenges of the prior year’s equity plan to inform the development of this year’s equity plan. This feedback could be gathered during PTA meetings, staff meetings, or via surveys sent to stakeholder
Not Yet Started | Completed Step 1 tab.
Step 2: Select Strategies & Plan for Implementation
Not Yet Started | Select strategies that are directly aligned to the root cause analysis.
Not Yet Started | Continue implementing strategies that were on track from previous Equity Plan
Not Yet Started | Select strategies that are measurable, evidence-based, and aligned to the district commitments in Lever 1, 2, or 5 of the Effective Schools Framework.
Not Yet Started | Select benchmarks that are directly aligned to the selected strategies, viable within district’s specific context, and are measurable.
Not Yet Started | Consider strategies for stakeholder engagement & input to ensure buy-in for the process & outcomes.
Not Yet Started | Completed Step 2 tab.
Step 3: Monitor Progress & Fidelity of Implementation (FOI)
Not Yet Started | Conduct a detailed formative equity progress check multiple times throughout the year (at least BOY, MOY, & EOY) with the progress monitoring team.
Not Yet Started | Use or develop a progress tracking sheet that indicates the equity gap and the benchmarks that are directly aligned to each strategy (see OPTIONAL tabs below).
Not Yet Started | Communicate progress of the equity plan implementation to stakeholders to continue to keep them informed of the district’s commitment to achieving equity. This could include sharing updates in district and school newsletters, at school meetings and functions, and as an agenda item at PTA meetings
Not Yet Started | <Optional> Complete Action Plan & Progress Tracking Tool tab.
Not Yet Started | <Optional> Complete Monitor Progress & FOI tab.
Not Yet Started | Completed Step 3 tab.
Step 4: Submit Completed Equity Plan to TEA
Not Yet Started | Equity Plan Submitted via ISAM successfully by required annual deadline.

## Step 1 Review Data (Reqd)
The column titles for this worksheet are in rows 2, 5, 12-13 and 18. They span cells A2 through D2, A5 through D5, A12 through D13, and A18 through D18. There is information in cells A3 through D4, A6 through D7, A8 through B8, A14 through D17, and A19 through D19. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
Step 1. Review Current Data and Conduct a Root Cause Analysis
Reflection guidance for LEAs who have an existing Equity Plan For LEAs who do not have an existing Equity Plan, skip to the next section with root cause identification. | 1. Did the aligned strategy to eliminate the idenfied gap accomplish the desired equity goal according to the performance measure target? | 2. How will you continue implementing your existing strategy with enhancements or choose a new strategy for next year's equity plan? | 3. What lessons have you learned in the past two years and how will those lessons inform next year's equity plan?
| Our plan has helped in recruiting more qualified teachers in reading and math. We are a Pre K-12 campus that has historically struggled to recruit core content teachers. Teacher retention has also been a challenge. Although it isn't included in our previous equity plan, we are currently reviewing our professional development activities and Title funding to better support new, inexperienced, and out-of-field teachers. | We are choosing two new strategies for next year's equity plan. We are going to shift our focus to developing our teacher capacity and effectiveness through professional development oppportunities. We are also planning on implementing a data driven process that will allow campus leaders to evaluate teacher effectiveness based on academic student growth data. | We have learned that often times our problems around recruiting and retaining teachers are out of our realm of control. We want to shift our focus to building campus leader capacity in developing systems to increase effective teachers on our campuses.
Using the rows below, capture any potential root causes that the data revealed. In the first row of each category, write the highest leverage root cause for the district to address. (Note: you may not have root causes in all four sections attract, assign, support, retain).
Root Causes as They Relate to ATTRACTING Effective Teachers | Root Causes as They Relate to ASSIGNING Effective Teachers | Root Causes as They Relate to SUPPORTING Effective Teachers | Root Causes as They Relate to RETAINING Effective Teachers
District does not have a mentoring or support program to support out of field teachers that have been reassigned | District has no system in place to place teachers strategically. | District has a high number of inexperienced teachers who are not appropriately prepared to serve African-American, Hispanic and Economically Disadvantaged students. | The retention rate for teachers is very low, with majority of teachers in their first 5 years.
District reputation and accountability ratings keep applicants from applying for positions. | Principals are not fully aware of their teachers strengths and weaknesses in relation to student growth. | The district has experienced regular turnover of instructional leadership and/or campus administration which heavily impacts the continuous and consistent support of teachers.
District does not have a plan in place to support new, uncertfied, out of field and inexperienced teachers with completing certification requirements or with tailored professional development based on teacher effectiveness data that is available to all administrators/instructional leaders.
Prioritization of Root Causes & Rationale
Based on the identification of root causes in the previous section, which category or categories (i.e. attracting, assigning, supporting, and/or retaining) are of the highest priority to address in your Equity Plan? These root causes will be the foundation for choosing strategies in Step 2.
Prioritized Category 1: | Supporting Effective Teachers
Rationale for Prioritized Category 1: Add a narrative for your team's rationale for prioritizing this first root cause | Our current teaching staff includes a large number of teachers with under five years experience. We are also staffed with several teachers going through the alternative teacher certfication program. Our professional development in the past has focused on curriculum, classroom management, and lesson planning. Our teachers are not provided with learning opportunities that allow them to be exposed to a variety of teaching strategies and differentiation techniques.
Prioritized Category 2: | Supporting Effective Teachers
Rationale for Prioritized Category 2: Add a narrative for your team's rationale for prioritizing this second root cause | We do not currently have a system in place for supporting new, uncertified, inexperienced, and out-of-field teachers in our small district. Our district experiences high turnover, mostly due to being in an isolated and remote area, and teachers find positions with higher pay and other opportunities in larger, nearby districts. We also experience turnover with administrators and instructional leaders.
Based on your analysis, now draft your problem statement with a focus on the challenge of attracting, assigning, supporting, or retaining effective, experienced, and in-field teachers in the highest need campuses serving low-income, African-American, and Hispanic students. Provide at least one root cause that is aligned to the problem statement as it relates to attracting, supporting and retaining effective teachers. Be sure the root cause analysis (RCA) reflects district, campus, and teacher levels.
Problem Statement: (The text you provide in the following cell will auto-populate on Step 3) | The district does not have a professional development plan in place for tailored and continuous implementation support for new, inexperienced, and out-of-field teachers (including a plan to assist them in completing any certification requirements) that can be monitored and sustained in the case of campus administration and/or instructional leadership turnover.

## Step 2 Plan for Impl. (Reqd)
The column titles for this worksheet are in rows 2-5. They span cells A2 through K5. There is information in cells A6 through E6, and A7 through K8. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
Step 2. Select Strategies & Plan for Implementation
Problem Statement (From Step 1): | The district does not have a professional development plan in place for tailored and continuous implementation support for new, inexperienced, and out-of-field teachers (including a plan to assist them in completing any certification requirements) that can be monitored and sustained in the case of campus administration and/or instructional leadership turnover. |  |  |  | This section should include your high-level plan for your district. When you move to step 3, you'll plan implementation with more granularity for each (sub)strategy.
Root Cause Category (from Step 1) | Identified Root Cause (from Step 1) | Selected Equity Plan Strategies | ESF Lever | District Commitment | Year 1 Mid-Year Milestone(s) | Year 1 End-of-Year Milestone(s) | Year 2 Mid-Year Milestone(s) | Year 2 End-of-Year Milestone(s) | Optional Year 3 Mid-Year Milestone(s) | Optional Year 3 End-of-Year Milestone(s)
What highest leverage root cause(s) have you identified to address? | Enter the your identified root cause(s) for this category in Step 1. | What strategy will you implement locally to address the identified root cause problem? | Which ESF Lever most closely aligns to your identified root cause? | Based on the ESF Lever chosen in column D, you'll want to input the District Commitment that most closely aligns to your intended strategy
Root Causes as They Relate to SUPPORTING Effective Teachers | District does not have a plan in place to support new, uncertified, out of field and inexperienced teachers with completing certification requirements and/or with tailored professional development based on teacher effectiveness data that is available to all administrators/instructional leaders. | District will create and implement professional development opportunities to support identified needs of targeted staff - uncertified, out of field, inexperienced and ineffective teachers - at all levels. District may utilize their ESC or other service provider to assist in the planning. | Lever 2 Strategic Staffing | District policies and practices ensure that campuses have effective, well-supported teachers. | By December, district will task administrators and instructional leaders to create a district professional development plan based on teacher effectiveness data available, including: *calibrated process and evaluation system (i.e. walkthrough data, timeline for review) *coaching and feedback *lesson plan reviews *continuous performance data *evaluations (i.e. student, teacher) | By end of school year, administration will: *Assess mid-year needs to continue to plan and implement PD series for summer and BOY/Fall PD *Evaluate Spring PD impact, teacher/coaching feedback, lesson plan review feedback, walkthrough data, local and state assessment data, etc.). *Have data and planning available for new administration in the case of turnover. | By December, evaluate the impact of Summer thru Fall PD provided to targeted teachers. *Continue to monitor in order to identify additional needs for Spring PD implementation *Assign mentors or content specialists to assist staff most in need of support based on mid-year walkthrough and other local data. *Collect data to make available to campus and district administration. | By end of school year, review & evaluate PD implementation. Administration will assess mid-year needs to continue and/or adjust PD plan and implement PD series for summer and BOY/Fall PD. All data and planning will be available for new administration in the case of turnover. *Spring PD impact *Teacher feedback *Coaching feedback *Lesson plan review feedback *Walkthrough data *Local and state assessements | Continue to work with teacher mentors to reevaluate and adjust mid-year professional growth needs. District / Campus leaders, mentors, and teachers will work together to implement instructional best practices based on two years of data. | By end of school year, staff surveys and student & teacher performance data will be analyzed to identify the impact of all equity plan strategies.

## Step 3 Progress Monitor (Reqd)
Step 3. Plan Progress Monitoring
Create a Sustainable Team & Structure: The district team, once created, will establish a time & place to collect and review evidence of progress toward each goal and strategy. There should also be meetings scheduled in advance to review data throughout the year to monitor progress. In addition to the table below, the Progress Monitoring Team may also consider using the OPTIONAL tabs for Monitoring Progress toward reaching the identified goals.
Proposed Equity Plan Progress Monitoring Team |  |  | Responsibilities (consider point-person(s) for tasks, deadlines, data management & analysis, and meeting preparation)
John Smith: Superintendent |  |  | Research and provide professional development opportunities for both campus leaders and instructional staff.
Patty Jones: Director of Instruction |  |  | Documentation and collection of data for each strategy. Monitoring implementation of new instructional strategies and data driven systems.
Sue Fuentes: Campus Principal |  |  | Implementation and monitoring at the campus level of proposed strategies. Assist with data collection.
Jerry Sims: Teacher |  |  | Implementation of proposed strategies. Support new or inexperienced teachers in the implementation.
Tiffany Black: Teacher |  |  | Implementation of proposed strategies. Support new or inexperienced teachers in the implementation.
Use the list of strategies and milestones from Step 2 Selecting Strategies to help you complete the blank Progress Monitoring Plan Template below. Each strategy that you have chosen should have its own progress monitoring plan; record them in the top left corner of the Progress Monitoring Plan Template. Some strategies may be complex; thus, it may be useful to break them into smaller sub-strategies. Your team should discuss each strategy in turn and make sure that the final progress monitoring plan has enough detail so that someone who is unfamiliar with your equity plan can understand how the strategy will be implemented in your district.
Problem Statement: | The district does not have a professional development plan in place for tailored and continuous implementation support for new, inexperienced, and out-of-field teachers (including a plan to assist them in completing any certification requirements) that can be monitored and sustained in the case of campus administration and/or instructional leadership turnover. |  |  |  | Long-Term Outcomes: (i.e. the changes your team expects to see in 2+ years) | Students from all of the sub-population groups will be performing at a high level and meeting all targets evaluated. There will not be a gap in performance between groups. Campus leaders will have the data needed to make informed decisions on staffing and assignments. Teacher capacity and effectiveness will be increased through targeted professional development opportunities.
Root Cause | Strategies & Substrategies | Year 1 Mid-Year Milestone(s) |  |  | Year 1 End-of-Year Milestone(s) |  | Year 2 Mid-Year Milestone(s) |  | Year 2 End-of-Year Milestone(s) |  | Optional Year 3 Mid Year Milestone(s) |  | Optional Year 3 End of Year Milestone(s)
What highest leverage root cause(s) have you identified to address? | What strategies and substrategies will you implement to address this root cause? | What are the next steps you will take to implement this strategy and achieve the outcome(s)? | If your strategy is well implemented, what will you see in up to 6 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 6–12 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 12–18 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 18–24 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 24-36 months? | What data will you collect to help you know if this strategy is working? | If your strategy is well implemented, what will you see in 36-48 months? | What data will you collect to help you know if this strategy is working?
District does not have a plan in place to support new, uncertfied, out of field and inexperienced teachers with completing certification requirements or with tailored professional development based on teacher effectiveness data that is available to all administrators/instructional leaders. | *District will create and implement professional development opportunities to support identified needs of targeted staff - uncertified, out of field, inexperienced and ineffective teachers - at all levels. *District may utilize their ESC or other service provider to assist in the planning. | 1. Evaluate current needs for winter professional development plans. 2. Develop specific training based on most recently collected data. 3. Schedule and deliver PD based on the needs of targeted staff. 4. Draft a Summer PD plan for next year. | 1. 100% of identified staff will have completed tailored training. 2. 100% of identified staff will have, together with their instructional leader(s), developed an individualized two-year professional development plan. 3. All walkthrough and PD documentation will be compiled and accessible to new administrators for the next school year. | *Targeted teachers will demonstrate implementation of specific PD best practices as measured by campus leadership observation and feedback data, including teacher survey data. *T-TESS individual PD plans. *Professional development records/attendance/certificates of completion. *Formative local student assessment data. | 1. 100% of identified staff will have completed tailored training. 2. 100% of identified staff will have, together with their instructional leader(s), reassessed their individualized two-year professional development plan to adjust, as needed, for year 2. 3. All walkthrough and PD documentation will continue to be compiled and accessible to new administrators for the next school year; identify areas of reinforcement and refinement to the process. 4. Instructional leaders and administrators will begin to develop pre-determined exit criteria for teachers who meet specific targets, as well as criteria for new teachers by end of Year 2. | *Targeted teachers will demonstrate implementation of specific PD best practices as measured by campus leadership observation and feedback data, including teacher survey data. T-TESS individual PD plans *Professional development records/attendance/certificates of completion *Formative / Summative student assessment data | 1. Finalized exit criteria will be used to exit teachers 2. Identify teachers who meet the exit criteria 3. At least 90% of all teachers on two-year PD plans will have successfully met exit criteria | *Targeted teachers will demonstrate implementation of specific PD best practices as measured by campus leadership observation and feedback data, including teacher survey data. T-TESS individual PD plans *Professional development records/attendance/certificates of completion. *Formative / Summative student assessment data *Exit criteria data | 1. Finalized exit criteria will be used to exit teachers 2. Identify teachers who meet the exit criteria 3. At least 90% of all teachers on two-year PD plans will have successfully met exit criteria |  | 1. Continue to support and mentor new staff, ineffective staff, and those who have not exited from their two-year growth plan. 2. Refine current PD plans and individual teacher growth plans. 3. Mentor teachers who have not yet met certification requirements, or who have not exited. | *Targeted teachers will demonstrate implementation of specific PD best practices as measured by campus leadership observation and feedback data, including teacher survey data. *T-TESS individual PD plans *Professional development records/attendance/certificates of completion *Formative / Summative student assessment data. *Exit criteria data | 1. Continue to support and mentor new staff, ineffective staff, and those who have not exited from their two-year growth plan. 2. Refine current PD plans and individual teacher growth plans. 3. Mentor teachers who have not yet met certification requirements, or who have not exited. | *Targeted teachers will demonstrate implementation of specific PD best practices as measured by campus leadership observation and feedback data, including teacher survey data. *T-TESS individual PD plans *Professional development records/attendance/certificates of completion *Formative / Summative student assessment data *Exit criteria data

## Action Plan & Progress Tracking
The column titles for this worksheet are in rows 2 through 4 and 10 through 11. They span cells A2 through N4, and A10 through N11. There is information in cells A5 through A9. The remaining cells have not been filled in. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
This tab is OPTIONAL and can be used for internal district planning and instructions as needed.
Equity Action Plan and Progress Tracking Tool (For each six month cycle, make a copy of this tab and edit as necessary.)
| Strategy #1 |  | Strategy #2 |  | Strategy #3 |  | Strategy #4 |  | Strategy #5 | Strategy #6
Selected Strategy
District Commitment
Annual Desired Milestone for Strategy
Desired Mid-Year Milestone
Barriers to address during this cycle
Action Plan-Milestones
Milestones | Year of Implementation | Selected Strategy | Timeline | Resources Needed | Person(s) Responsible | Metric/Evidence Used to Determine Progress Toward Milestone |  | Evidence Collection Date | Progress Toward Milestone | Necessary Adjustments/ Next Steps
Note on A3: This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on. ======

## Monitor Progress & FOI (OPTIONA
The column titles for this worksheet are in row 2 through 5. They span cells A2 through N5. There is information in cells A6, A8, A10, A12 through N12, A14, A16, A18 through N18, A20 and A22. The remaining cells have not been filled in where applicable. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
This tab is OPTIONAL and can be used for internal district planning and instructions as needed. This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on.
Monitor Progress and Fidelity of Implementation (For each six month cycle, make a copy of this tab and edit as necessary.)
Date Range: | Strategy and sub-strategy: |  |  | Type of outcome examined: |  | Mid-Year Y1 | End-of-Year Y1 | Mid-Year Y2 | End-of-Year Y2
Did our team do what was planned for this strategy? If not, what changes were made and why?
Did the data we collected help us to know if the strategy was implemented?
Describe any additional data we may need to help us understand this more or make better decisions.
To what extent have we made progress toward our goals? |  | Exceeded Goal(s) | Significant Progress |  | Some Progress |  | No Progress
Describe how we shared progress with stakeholders.
Do we need to make any adjustments at this time? If yes, please describe what changes we will make.
To what extent was the implementation of this strategy successful? Highlight the cell with your response and explain in row 19. |  | High level of success & fidelity of implementation |  | Some level of success and/or fidelity of implementation |  | No success and/or fidelity of implementation
If YES: How will we sustain this strategy? What factors need to be in place? If NO: Why wasn't the strategy implemented? What are the barriers to implementation? What are the next steps to ensure implementation or change the strategy? If it was implemented, but was only SOMEWHAT successful or did not lead to the expected outcome, was the strategy implemented with fidelity? What are next steps to take to improve outcomes?
Provide any additional insights we learned from completing this process or provide any additional information we think is necessary to understand our plan.
Note on A3: This will outline your district's plan for the first six months of implementation. End-of-Year Y1 is the second six months of implementation and so on. ======

## Data validation (hidden)
Lever | Lever_1_Strong_School_Leadership_and_Planning | Lever 2 Strategic Staffing | Lever 3 Positive School Culture | Lever 4 High-Quality Instructional Materials and Assessments | Lever 5 Effective Instruction
Lever 1 Strong School Leadership and Planning | 1.1. Develop campus instructional leaders with clear roles and responsibilities. | 2.1 Recruit, select, assign, induct, and retain a full staff of highly qualified educators | 3.1 Explicit school-wide behavioral expectations and culture routines | 4.1 Daily use of high-quality instructional materials | 5.1 Professional Development for Effective Classroom Instruction
Lever 2 Strategic Staffing | 1.2. Compelling and aligned vision, mission, goals, values focused ona safe environment, high expectations, and rigorous instruction. |  | 3.2 Proactive and responsive student support services |  | 5.2 Build teacher capacity through observation and feedback cycles
Lever 3 Positive School Culture | 1.3 Focused plan development and regular monitoring of implementation and outcomes |  | 3.3 Involving families and community |  | 5.3 Data-driven instruction
Lever 4 High-Quality Instructional Materials and Assessments | 1.4. The district provides the campus with adequate funding and sufficient control over their budget to ensure access to necessary resources for implementation of the school’s improvement plan and high-quality instruction to meet students’ learning needs. |  |  |  | 5.4 MTSS for students with learning gaps
Lever 5 Effective Instruction