## CONTROLSHEET (hidden)
Yes | 1 | Ordered | 1.1 | 1 - Not Started | No Progress
No | 2 | Voluntary | 2.1 | 2 - Planning for Implementation | Some Progress
| 3 |  | 3.1 | 3 - Beginning Implementation | Significant Progress
| 4 |  | 4.1 | 4 - Partial Implementation | Met
| 5 |  | 5.1 | 5 - Full Implementation
| 6 |  | 5.3
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## DCSI Attestation Stmnt
TEA Academy Elementary
2020-2021 District Coordinator of School Improvement (DCSI) Superintendent Attestation
The superintendent must name a District Coordinator of School Improvement (DCSI) if their local education agency (LEA) meets one or more of the following criteria: • the LEA, including those evaluated under alternative education accountability, was assigned an overall rating of F or must engage in unacceptable interventions due to TEC §39A.0545(b) or (c) or was assigned an overall rating of D or D in a domain; • a campus within the LEA, including alternative education campuses, was assigned an overall rating of D or F or D in a domain; • a campus was identified as in need of Comprehensive Support, Targeted Support, or Additional Targeted Support; or • the LEA or campus described above has an appeal of a 2020 accountability rating pending.
The DCSI oversees the work of school improvement as a required member of the Campus Intervention Team (CIT), leads and participates in the needs assessment, including the Effective Schools Framework (ESF) self-assessment and ESF Diagnostic process, improvement planning, and monitoring processes, and ensures requirements and submissions are completed on time. The DCSI supports campus and district improvement by ensuring that the district creates the conditions for campus implementation of best practices. The district commitments in the ESF describe what the district does to create the foundations upon which school-based best practices are built, and the district’s actions are captured in the Targeted Improvement Plan (TIP). The DCSI needs to be in a position to impact and/or influence the ESF district commitments aligned to campus needs. DCSIs are principal supervisors or other district-level leaders with direct responsibility for campuses that have been identified for improvement under state and/or federal accountability. It is strongly encouraged that the DCSI be the supervisor of the principal for the campus with an unacceptable performance rating. If the DCSI is not the principal supervisor, the principal supervisor is required to be a member of the CIT per Texas Administrative Code §97.1063(b)(2). I, the superintendent of schools, attest that I have read the DCSI Job Description, and that the DCSI selected can perform all the duties included in the job description.
DSCI Job Description
Campus Name: | District Coordinator of School Improvement (DCSI) Name, Role:
TEA Academy Elementary | Jaime Cervantes, Assistant Superintendent
Campus Number: | Superintendent Name:
123456789 | Ashley Mezger
Date:
2020-08-25

## Foundations
CAMPUS INFORMATION
Complete all campus information, including all names for the roles listed. In row 6, please indicate if this Targeted Improvement Plan is the implementation of a Turnaround Plan. If so, please put the school year that the TAP was first implemented. Please indicate if you were ordered to implement the TAP or if implementation was voluntary.
District Name | Nuss ISD | Campus Name | TEA Academy Elementary | Superintendent | Ashley Mezger | Principal | Steve Kane
District Number | 123456 | Campus Number | 123456789 | District Coordinator of School Improvement (DCSI) | Jamie Cervantes | ESC Number | 21
Is this a Turnaround Implementation Plan? | Yes | What Year was the TAP first implemented? | 2020-2021 | Was TAP Implementation Ordered or Voluntary? | Voluntary | ESC Support | Annie Hall
ASSURANCES
Enter the name of the person in each role below and the date this tab was completed. Please update row 13 with the Board Approval Date when the TIP has been board approved.
DCSI |  | I, the District Coordinator of School Improvement, attest that I will provide or facilitate the provision of all the necessary district-level commitments and support mechanisms to ensure the successful implementation of the Targeted Improvement Plan for this campus. I understand I am responsible for the implementation of all intervention requirements. If I am the principal supervisor, I understand I am responsible for ensuring the principal carries out the plan elements as indicated herein. |  |  |  | Jaime Cervantes, 08/25/2020
Principal Supervisor * Only necessary if the DCSI is NOT the Principal supervisor. |  | I, as supervisor of the principal for this campus, attest that I will coordinate with the DCSI to provide or facilitate the provision of all the necessary district-level commitments and support mechanisms to ensure the principal I supervise can achieve successful implementation of the Targeted Improvement Plan for this campus. I understand I am responsible for ensuring the principal carries out the plan elements as indicated herein. |  |  |  | Ashley Mezger, 08/25/2020
Principal |  | I, as principal for this campus, attest that I will coordinate with the DCSI (and my supervisor, if they are not the same person) to use the district-provided commitments and support mechanisms to ensure the successful implementation of the Targeted Improvement Plan for this campus. I agree to carry out the plan elements as indicated herein. |  |  |  | Steve Kane, 08/25/2020
Board Approval Date | Please update Board Approval date here. TIPs must be Board approved by the December 18th submission.
DATA ANALYSIS
Using your accountability data from 2019 (see link in Column G) and any relevant student achievement data from 2019-2020, set reasonable goals in each domain (1, 2B and 3). Include which special student groups you will be monitoring for progress. Include CCMR goals, if applicable. | [5 empty] | https://rptsvr1.tea.texas.gov/perfreport/tapr/2019/index.html
Data Analysis Questions | What accountability goals for each Domain has your campus set for the year? Be sure to include how you determined the goal for each domain and how these goals will impact your overall Accountability Rating. |  |  | Domain 1: For the 2020/2021 school year, our campus will increase our Domain 1 component score from a 28 (scaled score of 56) to a 41 (scaled score of 70) by increasing percent Approaches to 70%, Meets to 36%, and Masters to 16%. This will support our campus in achieving an overall C rating for 2021. Rationale: We have seen other campuses in our district achieve these results, and so believe they are feasible for us. By our campus focusing on strong instructional leadership for our CLT team members and focusing on strong lesson plans, and observation and debrief cycles, we can achieve these results.
Domain 2B: We will be focusing on Domain 2B. Our goal is to reach a component score of 41 (scaled 74) specifically for our econ dis students in 2021. Rationale: We have an Econ Dis percentage of 80%. We need to focus on campus relative performance this year. We know we can prove the possible for our students and ensure that our students can achieve at similar or higher levels compared to other schools with similar demographics.
Domain 3: We will increase our Domain 3 score of 31 (scaled score of 63) to a score of 50 (scaled score of 70) in 2021. Rationale: Our ELs population is represented by 40% of our students and the campus is having difficulty meeting the ELPs component of this domain. Additionally, none of the subgroups met their goals in the Student Achievement component of this Domain. Data indicates that our campus needs to implement differentiated instructional strategies to help our students in achieving the ELPs indicator and in earning at least a Meets level.
| What changes in student group and subject performance are included in these goals? |  |  | Domain 1: We need to focus on our G4 writing course. Our data is particularly low in this area, and it is impacting our student outcomes. Additionally, we need to prioritize moving more of our students to the Master's level across all courses. Lastly, our Hispanic student population is struggling in all content areas, and we need to ensure we are supporting our ELs with their achievement.
Domain 2: We are prioritizing our Eco Dis population and their achievement across the board for Domain 2.
Domain 3: We are targeting our Eco Dis, Hispanic and Sped Populations for Domain 3. We also need to prioritize the achievement for our ELs as our campus' TELPAS data is very low and indicates our ELs are not making adequate progress.
| If applicable, what goals has your campus set for CCMR and Graduation Rate? |  |  | N/A
CAMPUS FOCUS AREAS
Use information from your Reflective Prioritization Activity and ESF Diagnostic (if available) to complete the following section.
Essential Action |  |  |  |  | Implementation Level (1 Not Yet Started - 5 Fully Implemented)
1.1 Develop campus instructional leaders with clear roles and responsibilities. |  |  |  |  | 2 - Planning for Implementation
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators. |  |  |  |  | 3 - Beginning Implementation
3.1 Compelling and aligned vision, mission, goals, and values focused on a safe environment and high expectations. |  |  |  |  | 2 - Planning for Implementation
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence. |  |  |  |  | 3 - Beginning Implementation
5.1 Objective-driven daily lesson plans with formative assessments. |  |  |  |  | 2 - Planning for Implementation
5.3 Data-driven instruction. |  |  |  |  | 2 - Planning for Implementation
PRIORITIZED FOCUS AREAS
Complete each section below (please refer to your RPA): Essential Action: From the drop-down menu, select 2-3 Essential Actions the campus will prioritize in the 2020-2021 school year. Rationale: Explain the reason(s) this campus chose to focus on these Essential Actions this year. Capacity Building: For each prioritized focus area selected, list any internal/external capacity building efforts or cohorts in which you will participate this year. You may refer to the Vetted Improvement Programs found here: https://texasesf.org/vetted-programs/ Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face throughout the year. Desired Annual Outcome: For each prioritized focus area selected, create an annual goal that is specific, measurable, attainable, and realistic. District Commitment Theory of Action: For each prioritized focus area selected, list what the district will do to support the campus to achieve its desired annual outcome. Be sure to reference the District Commitments found in the ESF located here: https://texasesf.org/framework/
|  | Prioritized Focus Area #1 |  | Prioritized Focus Area #2 |  | Prioritized Focus Area #3
Essential Action |  | 1.1 |  | 5.1
Rationale |  | We want to create clear roles and responsibilities for the members of the leadership team and provide greater clarity to ILT members on how to lead their departments and grade-levels.
How will the campus build capacity in this area? Who will you partner with? |  | We will partner with the New Leaders cohort to clearly define the roles and responsibilities of all campus leaders.
Barriers to Address throughout this year |  | There is a mindset barrier around valuing and understanding the need to shift roles and responsibilities for CLT. This has resulted in leadership team members prioritizing other items and not attending meetings and/or trainings and the creation of meeting agendas. There is a resource barrier of CLT members being trained under time management and having the skill set to prioritize highest leverage actions for school improvement.
How will you communicate these priorities to your stakeholders? How will create buy-in? |  | The ILT, teachers, and parent committee will be involved in the process of defining clear roles and responsibilities of those in leadership roles. We will share these R+R in staff meetings to gather feedback.
Desired Annual Outcome |  | Members of the ILT observe classroom instruction, debrief observations with teachers, review lesson plans, and provide teachers with bite-sized, actionable feedback, all on a weekly basis.
District Commitment Theory of Action |  | If the district provides opportunities for ongoing support to principals and members of the ILT, as well as funds for the New Leaders cohort program, then campus leadership will have the tools they need to support teachers on a consistent basis, thereby improving student outcomes. |  | If….then, |  | If….then,

## Student Data Tab
|  | Campus Name: | TEA Academy Elementary | Campus Number: | 123456789
STUDENT DATA
"To complete the Student Data Tab, please enter data for all STAAR tested courses. - For Domain 1, enter the 2019 STAAR results for each tested course. You can enter the Total % of assessments at Approaches/Meets/Masters for your campus in column H in the form App/Meets/Ma (for example: 60/20/10). If you prefer to enter the data by each grade-level, you may add rows to accommodate each grade. If you administered a baseline assessment, please enter the data from that assessment in Column I. Enter the Total % of tests at each level of proficiency: Approaches, Meets, Masters. For each cycle, please enter Assessment Type. Remember to use comparable, STAAR-aligned assessments for each cycle. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. Please enter a Summative Goal as well. - For Domain 3, you will choose 2-4 targets to track this year. You can choose 1-2 targets from the Academic Achievement Indicators, 1-2 targets from the Student Success Indicators or a combinations of targets from both areas. Please indicate if you are choosing Academic Achievement or Student Success Indicators in Column B. . Please indicate if you are choosing Academic Achievement or Student Success Indicators in Column B. You will choose which tested subjects to track for these indicators. Your TEA Specialist can support you in selecting these focus areas. Just like in Domain 1, please include the 2019 results for each selected target group. If you administered a baseline assessment, please enter the data from that assessment in Column I. Enter the Total % of tests at each level of proficiency. Please enter a Summative Goal as well. If you are choosing to track Academic Achievement- Track Meets ONLY If tracking Student Success (El/MS) track an average of Approaches, Meets and Masters (as one number) High Schools or K-12 campuses should use one number that is in relation to CCMR. For each cycle, please enter the Assessment Type. Remember to use comparable, STAAR-aligned assessments for each cycle. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. - You will also track your English Language Proficiency throughout the year. Just like in Domain 1, please include the 2019 TELPAS data. If you administered a baseline assessment, please enter the data from that assessment in Column I. For each cycle, please identify what assessment you are using to track the progress of students (as a proxy for TELPAS). You can adjust the data you provide, based on the data your campus collects. Enter the formative goal for that cycle. Once data is available, please update the Actual Result column. Please enter a Summative Goals as well. Please communicate with your TEA School Improvement Specialist if there are challenges in completing all portions of this data at each cycle due to the disruption of the school year in regard to COVID-19. ** To unfreeze panes, select the View tab and click the Freeze Panes button."
Core Metrics | Sub Metrics | Grade Level | Student Group | Subject Tested | Performance Level | Summative Assessment | % of Assessments
[7 empty] | 2019 Results | 2020 Baseline Data (Optional) | Cycle 1 |  |  | Cycle 2 |  |  | Cycle 3 |  |  | 2021 Accountability Goal
[9 empty] | Assessment Type | Formative Goal | Actual Result | Assessment Type | Formative Goal | Actual Result | Assessment Type | Formative Goal | Actual Result | Summative Goal
1. Domain 1 | % of Students at Approaches, Meets and Masters | 3rd-5th | All | Reading | Approaches | STAAR | 55 | 50 | District Interim | 60 | 55 | District Interim | 65 |  | Released STAAR | 70 |  | 75
|  | 3rd-5th | All | Reading | Meets | STAAR | 22 | 20 | District Interim | 30 | 25 | District Interim | 35 |  | Released STAAR | 40 |  | 45
|  | 3rd-5th | All | Reading | Masters | STAAR | 6 | 5 | District Interim | 10 | 10 | District Interim | 20 |  | Released STAAR | 25 |  | 30
|  | 3rd-5th | All | Mathematics | Approaches | STAAR | 63 | 55 | District Interim | 65 | 65 | District Interim | 70 |  | Released STAAR | 75 |  | 80
|  | 3rd-5th | All | Mathematics | Meets | STAAR | 24 | 20 | District Interim | 30 | 32 | District Interim | 35 |  | Released STAAR | 45 |  | 50
|  | 3rd-5th | All | Mathematics | Masters | STAAR | 4 | 2 | District Interim | 10 | 13 | District Interim | 15 |  | Released STAAR | 25 |  | 30
|  | 5th | 5th | Science | Approaches | STAAR | 57 | 50 | District Interim | 60 | 55 | District Interim | 65 |  | Released STAAR | 70 |  | 75
|  | 5th | 5th | Science | Meets | STAAR | 16 | 12 | District Interim | 20 | 22 | District Interim | 25 |  | Released STAAR | 35 |  | 40
|  | 5th | 5th | Science | Masters | STAAR | 3 | 0 | District Interim | 10 | 24 | District Interim | 15 |  | Released STAAR | 25 |  | 30
|  | 4th | All | Writing | Approaches | STAAR | 40 | 10 | District Interim | 25 | 20 | District Interim | 25 |  | Released STAAR | 35 |  | 50
|  | 4th | All | Writing | Meets | STAAR | 19 | 3 | District Interim | 10 | 8 | District Interim | 15 |  | Released STAAR | 25 |  | 25
|  | 4th | All | Writing | Masters | STAAR | 8 | 2 | District Interim | 5 | 2 | District Interim | 10 |  | Released STAAR | 15 |  | 15
2. Domain 3 Focus 1 | Focus 1 Components (Choose two targets in the Academic Achievement or Student Success indicators) | 3rd - 5th | Eco Dis | Reading | Meets | STAAR | 17 | 15 | District Interim | 25 | 20 | District Interim | 30 |  | Released STAAR | 35 |  | 38
|  | 3rd - 5th | Hispanic | Reading | Meets | STAAR | 21 | 18 | District Interim | 30 | 28 | District Interim | 35 |  | Released STAAR | 40 |  | 42
3. Domain 3 Focus 2 | Focus 2 Components (Choose two targets in the Academic Achievement or Student Success indicators) | 3rd - 5th | Special Ed (Current) | All | All | STAAR | 8 | 3 | District Interim | 15 | 10 | District Interim | 15 |  | Released STAAR | 20 |  | 25
|  | 3rd - 5th | Eco Dis | All | All | STAAR | 24 | 18 | District Interim | 25 | 28 | District Interim | 30 |  | Released STAAR | 35 |  | 40
4. Domain 3 Focus 3 | ELP Component (Minimum 25 students required) | All | English Learners (ELs) | TELPAS | All | TELPAS | 6% | 7% | District Interim | 20% | 18% | District Interim | 30% |  | Released STAAR | 40% |  | 40%

## Cycle 1 (Sept-Nov)
|  | Campus Name: | TEA Academy Elementary | Campus Number: | 123456789
CYCLE 1 90-DAY OUTCOMES (September - November)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: For each prioritized focus area, describe the specific, measurable goal the campus plans to achieve by the end of this cycle. Barriers: For each prioritized focus area, list the barriers to implementation the campus may face during this 90-day cycle. District Actions for this Cycle: For each prioritized focus area, list what the district will do during this 90-day cycle to support the campus to achieve the desired outcome. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 1.1 |  |  | 5.1 |  |  | 0
Desired Annual Outcome | Members of the ILT observe classroom instruction, debrief observations with teachers, review lesson plans, and provide teachers with bite-sized, actionable feedback, all on a weekly basis. |  |  | 0 |  |  | 0
Desired 90-day Outcome | ILT is observing teacher instruction, debriefing observations, reviewing lesson plans, and providing teachers bite-size, high-leverage feedback at least 2x each month.
Barriers to Address During this Cycle | Time management due to BOY activities related to implementing multiple formats of instruction this cycle due to COVID-19. Mindset challenges around shifting roles of ILT and new responsibilities. Building ILT skill in observation/debrief cycle and lesson plan review.
District Actions for this Cycle | The DCSI Supervisor will observe campus operations and classroom instruction, and provide feedback and coaching to the principal and members of the ILT around classroom observations and debriefs. The district will also financially support the campus participating with the New Leaders cohort.
District Commitment Theory of Action | If the district provides opportunities for ongoing support to principals and members of the ILT, as well as funds for the New Leaders cohort program, then campus leadership will have the tools they need to support teachers on a consistent basis, thereby improving student outcomes. |  |  | If….then, |  |  | If….then,
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Essential Action | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
DCSI and Principal will review written roles and responsibilities of campus leadership team to verify if current and appropriate in view of possible changes since last SY. |  | 1.1 | 08/01 - 08/15 | Job Descriptions, Previously written roles & responsibilities | DCSI & Principal | Next Steps list developed during meeting between DCSI and Principal. | 2020-08-15 | Met
Principal will review current roles and responsibilities with ILT and share feedback from DCSI. New, finalized roles will be determined. |  | 1.1 | 08/01 - 08/15 | Job Descriptions, Previously written roles & responsibilities | Principal & APs | Finalized roles and responsibilities | 2020-08-15 | Met
Principal will review classroom observation schedules assigned to the ILT, and revise as needed. |  | 1.1 | 08/01 - 08/20 | Master Schedule | Principal | Observation schedules from ILT | 2020-08-20 | Met
Principal and ILT will review process regarding lesson plan submission, and revise as needed. |  | 1.1 and 5.1 | 08/01 - 08/20 | Previously written lesson plan submission process | Principal & APs, Instructional Coaches | Revised lesson plan submission process | 2020-08-27 | Met
During BOY activities, teachers will be informed of ILT's roles and responsibilities, the process for submitting lesson plans and receiving feedback, and the observation/debrief cycle. |  | 1.1 and 5.1 | 08/20 - 09/20 | Current ILT roles & responsibilities, current process for LP submission, and current process observation and feedback. | Principal & Grade-level chairs | BOY Activity Agendas indicating topics and who attended. | 2020-09-20 | Met
ILT members will receive initial and ongoing training and support from Principal and DCSI on classroom observation and debrief cycles. |  | 1.1 | 09/01 - 11/30 | Template for collecting evidence regarding classroom observation | Principal & APs, Instructional Coaches | Observation and Feedback process, and protocol and agenda for debrief conversations | 9/30, 10/30, 11/30 | Some Progress | We received initial training, but the follow-up and ongoing support has been challenging. We need to continue this work and protect our time to ensure these responsibilities are met; Principal needs to make time for ongoing coaching of ILT.
ILT members will receive initial and ongoing training and support from Principal and DCSI on lesson plan review and feedback protocol. |  | 1.1 and 5.1 | 09/15 - 11/30 | Lesson plan template and look-fors document | Principal & DCSI | Lesson plans with feedback from each ILT member | 9/30, 10/30, 11/30 | Some Progress | We need to norm on the time commitment for this task and re-norm on what actionable, bite-sized feedback looks like
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not? |  |  |  | We did not fully meet our 90-Day outcome. While we have been able to increase the amount of time we have spent observing and providing feedback on lesson plans, we have not been able to consistently meet the goal of 2x a month for each of these activities. One reason has been that there has been a shift in our roles, and it has taken some time for our CLT to get used to prioritizing instruction over classroom support. Additionally, we have not established a strong enough student culture that allows us to maximize time on instruction as opposed to putting out fires in teachers' classrooms.
Did you achieve your student performance goals (see Student Data Tab)? Why or why not? |  |  |  | We met our achievement goals in math but have not done so in the other areas. A reason for this is we have not been able to utilize consistent, effective data analysis and remediation or re-teaching for our students. We also have a lot of work to do in order to make up for the academic losses due to the school closure last year.
Review the necessary adjustments/next steps column above. What action steps from this cycle will you continue working on in the next cycle? What new action steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps
|  |  |  | ILT members will receive initial and ongoing training and support from Principal and DCSI on classroom observation and debrief cycles. ILT members will receive initial and ongoing training and support from Principal and DCSI on lesson plan review and feedback protocol. |  |  | Begin a series of classroom management trainings and coaching cycles for some of our less effective teachers.

## Cycle 2 (Dec-Feb)
|  | Campus Name: | TEA Academy Elementary | Campus Number: | 123456789
CYCLE 2 90-DAY OUTCOMES (December-February)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: For each prioritized focus area, describe the specific, measurable goal the campus plans to achieve by the end of this cycle. Barriers: For each prioritized focus area, list the barriers to implementation the campus may face during this 90-day cycle. District Actions for this Cycle: For each prioritized focus area, list what the district will do during this 90-day cycle to support the campus to achieve the desired outcome. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 1.1 |  |  | 5.1 |  |  | 0
Desired Annual Outcome | Members of the ILT observe classroom instruction, debrief observations with teachers, review lesson plans, and provide teachers with bite-sized, actionable feedback, all on a weekly basis. |  |  | 0 |  |  | 0
Desired 90-day Outcome | ILT is observing teacher instruction, reviewing lesson plans, and providing teachers feedback at least 3x each month.
Barriers to Address During this Cycle | Time management due to MOY activities (Benchmark testing and analysis, extra-curricular activities). Ensuring Principal has time and is able to coach ILT in these responsibilities.
District Actions for this Cycle | The DCSI Supervisor will continue observing campus operations and classroom instruction, and providing feedback and coaching to the principal and members of the ILT. DCSI will attend coaching conversations with Principal and members of ILT to provide feedback to Principal on her coaching.
District Commitment Theory of Action | If the district provides opportunities for ongoing support to principals and members of the ILT, as well as funds for the New Leaders cohort program, then campus leadership will have the tools they need to support teachers on a consistent basis, thereby improving student outcomes. |  |  | If….then, |  |  | If….then,
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
Principal and ILT will review evidence collected during previous cycle to determine if classroom observation schedules have been followed as designed, and discuss if changes are needed. |  | 1.1 | 12/07 - 12/18 | Observation Notes; Master Schedule | Principal & ILT | Updated classroom observation schedules | 2020-12-18
Principal and ILT will review evidence collected during the previous cycle to determine if lesson plan submission process is working, and discuss if changes are needed. |  | 1.1 and 5.1 | 12/07 - 12/18 | Lesson Plan Feedback forms; Current lesson plan submission process | Principal & ILT | Next Steps list developed during meeting between Principal and ILT. | 2020-12-18
Principal and ILT will attend district-provided leadership training on coaching strategies. |  | 1.1 | 2021-01-04 | Pre-reading for district training | Principal & ILT | Coaching Strategies; notes from the training | 2021-01-05
Principal will ensure she is coaching each member of ILT at least one time per week on the observation/feedback cycle. |  | 1.1 | 12/01 - 02/29 | Scheduled observations, observation forms, debrief agendas | Principal | Coaching notes from Principal's coaching of ILT members | 12/19, 01/23, 2/5, 02/12, 2/26
During leadership team meetings Principal and ILT will engage in a lesson plan feedback calibration activity to build skill in this area. |  | 1.1 and 5.1 | 12/01 - 02/29 | Lesson plans brought to meetings; lesson plan look-fors, feedback protocol | Principal | Leadership team meeting agenda, calibration activates, documented next steps | 12/14, 01/18, 2/1, 02/8, 2/22
Struggling and new teachers will attend classroom management series of trainings to build skill in this area |  | 1.1 and 3.1
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry-over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not?
Did you achieve your student performance goals (see Student Data Tab)? Why or why not?
Review the necessary adjustments/next steps column above. What Action Steps from this cycle will you continue working on in the next cycle? What new Action Steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps

## Cycle 3 (Mar-May)
|  | Campus Name: | TEA Academy Elementary | Campus Number: | 123456789
CYCLE 3 90-DAY OUTCOMES (March-May)
Essential Action: Pre-populates from the 'Foundations' tab. Desired Annual Outcome: Pre-populates from the 'Foundations' tab. For each Prioritized Focus Area, please complete the following sections: Desired 90-Day Outcome: For each prioritized focus area, describe the specific, measurable goal the campus plans to achieve by the end of this cycle. Barriers: For each prioritized focus area, list the barriers to implementation the campus may face during this 90-day cycle. District Actions for this Cycle: For each prioritized focus area, list what the district will do during this 90-day cycle to support the campus to achieve the desired outcome. District Commitment Theory of Action: Pre-populates from the 'Foundations' tab.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 1.1 |  |  | 5.1 |  |  | 0
Desired Annual Outcome | Members of the ILT observe classroom instruction, debrief observations with teachers, review lesson plans, and provide teachers with bite-sized, actionable feedback, all on a weekly basis. |  |  | 0 |  |  | 0
Desired 90-day Outcome | ILT is observing teacher instruction, reviewing lesson plans, and providing teachers weekly feedback.
Barriers to Address During this Cycle | Time management due to EOY activities (Benchmark testing and analysis, Logistics of STAAR testing, extra-curricular activities). Ensuring the investment in lesson plan feedback and classroom observation cycles remains high at this point in the year.
District Actions for this Cycle | The DCSI Supervisor will continue observing campus operations and classroom instruction, and providing feedback and coaching to the principal and members of the ILT.
District Commitment Theory of Action | If the district provides opportunities for ongoing support to principals and members of the ILT, as well as funds for the New Leaders cohort program, then campus leadership will have the tools they need to support teachers on a consistent basis, thereby improving student outcomes. |  |  | If….then, |  |  | If….then,
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Step |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps
Principal will ensure she is coaching each member of ILT at least once every other week on the observation/feedback cycle. |  | 1.1 | 3/01 - 5/31 | Scheduled observations, observation forms, debrief agendas | Principal | Coaching notes from Principal's coaching of ILT members | 3/5, 3/19, 4/2, 4/9, 4/16, 4/23, 5/7
Principal and ILT will participate in joint observation rounds to ensure calibration on feedback |  | 1.1 | 3/01 - 5/31 | Master schedule, observation schedule | Principal & ILT | Observation notes and feedback | 3/5, 3/19, 4/16, 4/23
During leadership team meetings Principal and ILT will engage in classroom observation debrief conversation calibration activities to build skill in this area. |  | 1.1 | 3/01 - 5/31 | Scheduled observations, observation forms, debrief agendas | Principal & CLT | Notes from Leadership team meetings, next steps captured | 3/8, 3/22, 4/5, 4/19, 5/3
Principal will provide feedback to members of ILT on lesson plan feedback at least 2x per month |  | 1.1 | 3/01 - 5/31 | lesson plan feedback from ILT, lesson plan look-fors, feedback protocol | DCSI & Principal | Feedback provided to ILT, next steps captured | 3/8, 3/22, 4/5, 4/19, 5/3
REFLECTION and PLANNING for NEXT 90-DAY CYCLE
At the end of this cycle, please reflect on the implementation of your Targeted Improvement Plan thus far by responding to the questions below. Be sure to explain whether your outcomes and student performance goals were met and why or why not. List any action steps you will carry-over to the next cycle and any new action steps you have discovered necessary for the next cycle. Be sure to add these action steps into the next cycle's action plan.
For each of the Prioritized Focus Areas, did you achieve your desired 90-day outcome? Why or why not?
Did you achieve your student performance goals (see Student Data Tab)? Why or why not?
Review the necessary adjustments/next steps column above. What Action Steps from this cycle will you continue working on in the next cycle? What new Action Steps do you need to add to the next cycle? |  |  |  | Carryover Action Steps |  |  | New Action Steps
END OF YEAR REFLECTION
Please reflect on the year's implementation of your Targeted Improvement Plan by responding to the questions below. Be sure to explain whether your campus achieved the desired annual outcome for each Prioritized Focus Area and why or why not.
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action | 0 |  |  | 0 |  |  | 0
Desired Annual Outcome | 0 |  |  | 0 |  |  | 0
Did the campus achieve the desired outcome? Why or why not?

## Cycle 4 (Jun-Aug)
|  | Campus Name: | TEA Academy Elementary | Campus Number: | 123456789
CYCLE 4 90-DAY OUTCOMES (June-August)
The purpose of this 90-Day action plan is to prepare for the upcoming school year. The essential actions the campus prioritizes may have changed based on progress made in the school year or based on ESF diagnostic results. Please complete this portion of the plan by reflecting on your campus's progress this year and identifying your focus areas for next year. This tab serves as the foundation for next year's Targeted Improvement plan. Complete each section below: Essential Action: From the drop-down menu, select 2-3 Essential Actions the campus will prioritize in the 2021-2022 school year. Rationale: Explain the reason(s) this campus chose to focus on these Essential Actions during the 2021-2022. Communication: Describe how you will communicate your priorities to your stakeholders and how you will create buy-in from key stakeholder groups. Desired Annual Outcome: For each prioritized focus area selected, create your annual goal that is specific, measurable, attainable, and realistic. Desired 90-Day Outcome: For each prioritized focus area, describe the specific, measurable goal the campus plans to achieve by the end of this cycle (June-August) . Capacity Building: For each prioritized focus area selected, list any internal/external capacity building efforts or cohorts in which you will participate in during the 2021-2022. You can refer to the Vetted Improvement Programs found here: https://texasesf.org/vetted-programs/ Barriers: For each prioritized focus area selected, list the barriers to implementation the campus may face throughout the year. District Actions for this Cycle: List what the district will do to support the campus to achieve the desired outcome during this 90-day cycle . District Commitment Theory of Action: For each prioritized focus area selected, list what the district will do to support the campus to achieve its desired annual outcome. Be sure to reference the District Commitments found in the ESF located here: https://texasesf.org/framework/
| Prioritized Focus Area #1 |  |  | Prioritized Focus Area #2 |  |  | Prioritized Focus Area #3
Essential Action
Rationale
How will you communicate these priorities to your stakeholders? How will you create buy-in?
Desired Annual Outcome
Desired 90-Day Outcome
How will the campus build capacity in this area? Who will you partner with?
Barriers to Address throughout the year
District Actions for this Cycle
District Commitment Theory of Action
ACTION PLAN
In each row below, list the actions the campus is taking during this cycle to achieve its desired outcomes and address the identified barriers to implementation. For each action step, indicate: - the prioritized essential action it is aligned to, - the start date/end date during this specific cycle, - the resources needed to accomplish this task, - the person(s) responsible for ensuring task is accomplished, - the evidence that will be used to determine progress toward the action step, and - the date evidence will be collected. At the end of each cycle - For each action step: (1) select the progress review status from the drop down menu, and (2) describe what next steps will be taken during the next cycle. For each action that has not been MET, please update column J with necessary adjustments or next steps for this action step.
Action Steps |  | Prioritized Focus Area | Start Date/End Date | Resources Needed | Person(s) Responsible | Evidence used to Determine Progress toward Action Step (May be requested by Specialist) | Evidence Collection Date | Progress toward Action Step | Necessary Adjustments / Next Steps