## Turnaround Foundations
Campus Turnaround Plan
Campus Information
District Name: |  |  | Superintendent: | DCSI: | Board President:
Campus Name: |  |  | Campus Number: | Principal: | Principal Supervisor:
School Year Plan was Developed: |  |  | ESF Diagnostic Date: | ESF Facilitator: | Date of Board Approval:
Turnaround Method
Select the turnaround method your campus is pursuing. See the Description of Methods guidance document for more information.
Method |  | Description |  |  |  | Check one
School Improvement |  | Improve foundational practices at the campus by working with a vetted improvement program and/or developing an internal capacity building plan.
School Action-Reassign |  | Close the low-performing campus and reassign students to higher performing (A or B rated) campuses or new campuses.
School Action-Restart: District Managed |  | Restart a school by implementing the Accelerating Campus Excellence model or ACE-like model (including Accelerating Campus Excellence (ACE) turnaround plans).
School Action-Restart: Partner Managed |  | Restart a school with a Texas Partnership with an existing operator with a track record of success
School Action-New School: District-Managed |  | Create or phase in a new school managed by the district at a new or existing facility
School Action-New School: Partner Managed |  | Create or phase in a new school with a Texas Partnership at a new or existing facility
Outcomes
For each essential action, describe the current implementation level on the campus (using the ESF Diagnostic Summary Report) and what full implementation will look like on this campus. Reference the Key Practices in the Effective Schools Framework to develop the vision. Campuses should strive to be at or near full implementation within two years after implementing this Turnaround Plan for two years.
1.1 Develop campus instructional leaders with clear roles and responsibilities. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision
3.1 Compelling and aligned vision, mission, goals, values focused on a safe environment and high expectations. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision
5.1 Objective-driven daily lesson plans with formative assessments. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision
5.3 Data-driven instruction. | Current Implementation: Summary
Implementation Level At Diagnostic
Prioritized Focus Area from ESF Diagnostic?
Full Implementation: Vision

## dropdowns (hidden)
Impl level | Yes | EA nums
Full Implementation | No | 1.1
Partial Implementation |  | 2.1
Beginning Implementation |  | 3.1
Planning for Implementation |  | 4.1
Not Yet Started |  | 5.1
5.3
|  |  | Essential Action | Pre-Implementation | Implementation Year 1 | Implementation Year 2 | Implementation Year 3 and beyond
1.1 Develop campus instructional leaders with clear roles and responsibilities.
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators.
3.1 Compelling and aligned vision, mission, goals, values focused on a safe environment and high expectations.
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence.
5.1 Objective-driven daily lesson plans with formative assessments.
5.3 Data-driven instruction.
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These milestones must be included in the campus' current year TIP, Cycle 4
Note on Q17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Milestones in this column can be focused on sustainalibyt of systems implemented in years 1 and 2 of implementation. A campus that is ordered to implement a turnaround plan may modify the milestones in this column once they receive two consecutive acceptable ratings.

## School Improvement
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Improvement Turnaround Plan
District Commitment Theory of Action
In this section, describe the District Theory of Action and the District Commitments that will support the campus' essential actions found in the plan. The District Theory Commitment Theory of Action should address each of the Foundational Essential Actions and DDI.
System and Capacity Building
In this section, describe the efforts the campus and district will make to build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe areas in which you will build systems, skills, and capacity in district and campus staff. |  | What potential program or partners will the campus/district work with in this area? |  | When will this be a focus? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
Critical Implementation Milestones
In this section, describe the critical implementation milestones (high-level description of actions that will be completed) that the campus and/or district will meet in each year of implementation in order to achieve the vision of full implementation of each Essential Action shared on the Turnaround Foundations tab. Milestones for the 2-3 high leverage focus areas identified in the ESF Diagnostic must be addressed first, as these are the campus' largest gaps in practice and systems (and will have the greatest impact on the implementation of other Essential Actions). The milestones listed here must be included in each year's Targeted Improvement Plan. Add rows as needed.
Pre-Implementation | [5 empty] | Essential Action
Implementation Year 1 | [5 empty] | Essential Action
Implementation Year 2 | [5 empty] | Essential Action
Implementation Year 3 and beyond | [5 empty] | Essential Action
Milestones in this column can be focused on sustainability of systems implemented in years 1 and 2 of implementation. A campus that is ordered to implement a turnaround plan may modify the milestones in this section once they receive two consecutive acceptable ratings.
Budget and Financial Resources
Funds outlined in the budget table should include any supplemental costs required to implement the turnaround plan for 2 or more years. For example, salaries for teachers and principals should not be included; however, if the initiative calls for teacher stipends to cover extra duties, those costs should be accounted for in the table.
Category | Amount |  | Description
Payroll | 0
Professional Development | 0
Supplies and Materials | 0
Other Operating Costs | 0
Capital Outlay | 0

## School Action (SA)-Reassign
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Reassign
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. |  | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on the school reassignment plan. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop and finalize plans for student reassignment
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Establish school selection and enrollment process for student reassignment, including identification of target schools for student placement | District should establish a school assignment/selection and enrollment process for reassigned students that maximize opportunities for students and families to enroll in high-quality, best-fit schools. | - Summary of student reassignment/ enrollment process - List of target schools with information about performance levels and enrollment capacity
Develop and implement a strategy for supporting families with decision making support for student enrollment / reassignment. | Strategy should ensure that every family has access to information and case management support to evaluate options and make informed decisions about school reassignment/enrollment. | Summary of student enrollment support services
Establish plan for use of closed school facility (or process for determining the plan) | District should develop and clearly communicate short- and long-term plans for future use of the closed school facility. | External communication of facility plans
Year 1 - Planning Phase 3: Approve and finalize plans and goals for student reassignment to new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Finalize goals for student reassignment process | Reassignment process should include specific goals for evaluating success; including measures to determine number and/or percentage of reassigned students that enroll in higher-performing campuses.
District superintendent and board approves plans and policies for student reassignment process | Board approves reassignment plan and adopts new district enrollment policies (as necessary) to support plan implementation.
Year 1 - Planning Phase 4: Transition - Support transition planning for students and schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Develop and Implement a detailed implementation plan for the reassignment process | Detailed Implementation plan should address a comprehensive set of activities to support the reassignment of students to new campuses, as well as activities to support the smooth transition of the closing facility/campus.
Year 2 - Implementation: District implements reassignment with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Students attend new schools and school is closed
District implements reassignment implementation plan | Detailed Implementation plan should include activities during the transition school year to ensure all students are served in campus at school district |  | Reassignment implementation plan
Schools attended by students participate in formative school quality review process with third party technical assistance provider organization. | District partners with third party technical assistance provider organization to conduct a formative, on-site school review process aligned to the ESF framework. Review process provides formative feedback on school practices and alignment to new school academic model. |  | School review report

## SA-Restart, District Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Turnaround Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning and Implementation Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align restart strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Identify Project Teams and Committees | ACE Design Team / Project Lead – there must be a person(s) identified as project lead, with the authority (either by existing role or Superintendent designee) to make decisions and the C-level relationships to ensure the process moves at the appropriate speed. Most important departments in the planning/design phase include: Human Capital, School Leadership, Communications, Operations/Finance | - District project manager - Document that outlines district committee that will lead the work
Establish school program requirements | This will follow the five core pillars of the ACE model: (1) Strategic Staffing, (2) Instructional Excellence, (3) Extended Day, (4) Social and Emotion Learning, and (5) Community and Parent Partnerships. | One-pager on programmatic elements by ACE pillar; ongoing assessment of district's ACE implementation plans
Identify third-party implementation partner | Describe the third-party implementation partner that the district proposes to partner with or is partnering with. Describe the experience this partner has in supporting other campuses with the design and implementation of the specific ACE turnaround model. Describe, specifically, the activities that the partner will support the campus with. | Contract or MOU with third-party implementation provider
Year 1 - Planning Phase 2: Develop - Develop policies and systems for implementing ACE
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop campus administrator selection process | Districts should conduct a quantitative and qualitative analysis of current principals based on relative school performance vs. expected school performance. District leadership will be critical in helping to identify current leaders in the district that embody essential principal character traits. While many districts have a selection process outlined for the role of campus principal, districts may wish to use a condensed or modified selection process, in consideration that this will be a principal re-assignment and not an employee newly promoted to the principal role. The traditional process may also be condensed to ensure confidentiality prior to the broader announcement to the district and staff about the upcoming changes. | Administrator requirement blueprint
Develop Teacher Hiring/Selection Process | The teacher hiring process should begin with a quantitative and qualitative analysis of teacher performance across all teachers in the district. With this insight on performance, the newly selected campus principal will now have a target list for recruiting and assembling a team for the new campus. A principal will need to consider the composition not only of the overall teaching staff, but also within teams/depts/grade levels. | One-pager on programmatic elements by ACE pillar; ongoing assessment of district's ACE implementation plans
Develop principal and employee compensation structure. | Provide a detailed narrative description of the employment and compensation structure of the principal that details the principal's incentive payment and the assurance that the principal will continue to receive incentive payments over the next three years of implementation. Provide a detailed description of the employment and compensation structure of the teachers on the campus that details teacher incentive payments and the assurance that teachers will continue to receive incentive payments over the next three years of implementation. | Draft line-item ACE campus budget
Create a comprehensive budget plan | Districts will develop a line-item budget, including but not limited to, educator stipends, cost of extended day (transportation and enrichment programming), professional development, and social/emotional learning curriculum. | Draft line-item ACE campus budget
Develop an overall communication plan and strategy | A successful design and rollout of the ACE initiative with strong community and stakeholder support is contingent upon a district's ability to communicate effectively about the initiative. The communication plan should communicate key messages about why ACE is being implemented, who it impacts, and how it will be implemented. Districts should complete in the fall and early winter, so that materials are ready when official announcements begin. | Strategic Communication Plan
Year 1 - Planning Phase 3: Transition - Support transition planning for ACE model implementation
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Implement principal selection process | Select principal based on established recruiting/selection process. District should provide a narrative description of the principal's qualifications and why the district selected the principal to lead the ACE turnaround plan and the quantitative evidence that the principal has a demonstrated history of improvement in student academic growth at the campuses the principal has led or been a part of the management team at. | - Principal selected - Principal selection criteria document to outline selection process, rationale for selection, and principal resume
Implement principal contract with specific academic achievement improvements | District should execute a clear contract that contains the specific expected academic achievement improvements in each of the next three school years. | -Principal contract with detailed academic achievement improvements over the next three years
Implement teacher recruitment/hiring process | Hire teachers based on established recruiting/selection process. Provide a teacher roster by grade level, indicating which district the taught at in the preceding year. Provide evidence that at least 60 percent of the teachers on the roster had demonstrated instructional effectiveness during the previous school year. | Teacher hiring tracker
Identify data driven instructional practices | Describe the data-driven instructional practices to be implemented on the campus. Clearly link these practices to the specific actions within the Effective Schools Framework. | School design plan
Identify the system of observation and feedback for classroom teachers | Describe the system of observation and feedback for classroom teachers that will be implemented on the campus. Clearly link these practices to the specific actions of the Effective Schools Framework. | School design plan
Identify the curriculum for the school | Describe the curriculum that will be used at each grade level, how that curriculum was selected, and how teachers will be professionally developed to implement the curriculum. | School design plan
Identify the systems and practices to develop a positive school culture | Describe the systems and practices that the campus will implement to develop a positive school culture. Clearly link these practices to the specific actions of the Effective Schools Framework. | School design plan
Identify the systems and practices to ensure highly engaged families and communities | Describe the systems and practices that the campus will implement, including specific partnerships with specific parent and community groups, to ensure highly engaged families and communities. | School design plan
Identify extended learning opportunities | Describe the specific extended learning opportunities that will be afforded to students and how those students will be informed of those opportunities. | School design plan
Identify student services provided before and/or after school | Describe how the campus will provide student services before or after school. Describe, in detail, what services will be provided. | School design plan
Establish systems and capacity for formative, Effective Schools Framework-aligned progress monitoring during implementation year(s) | During the school year, the district will work with a third-party provider organization to conduct formative school visits to evaluate ACE model implementation and ESF-aligned school practices. School performance data will be tracked on either a 3-week or 6-week interim, depending on district processes, and will be compared where available, to 2018-2019 baseline data: (1) Student and staff attendance, (2) occurrences of discipline referrals, by sub population, and (3) academic interim assessments, in both K-2 and 3-8. | Progress Monitoring Plan
Year 2 - Implementation: ACE Implementation Fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School begins new school year as ACE campus
Establish afterschool enrichment opportunities for all interested students free of charge | These opportunities need to be open to all students, free of charge, and not solely University Scholastic League (UIL) activities. | Principal/District shared list of approved providers
Ensure transportation services | Ensure transportation services are in place for pickup after extended hour of instruction (typically around 4pm), as well as afterschool enrichment time (typically around 6pm). | Bus schedules and routes
Submit federal Afterschool Meals provider application for approval | Federal Afterschool Meals program allows eligible campuses to serve dinner and be reimbursed for those expenses. | Federal approval status
Complete parent / community engagement plan | Create schedule for PTA meetings/locations and determine adult basic education (ABE) and volunteer opportunities for parents and community members | Flyers, schedules, etc.

## SA-Restart, Partner Mangaged
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Partner Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a district authorizing policy. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Adopt district authorizing policies | District must adopt the TEA model authorizing policy if implementing partner-managed school models. In addition to authorizing policies, district should also consider if any "school choice policies" need adoption or revision to implement planned school actions. | District authorizing policy and board minutes
Conduct financial spending analysis in accordance with TEA requirements | LEAs pursuing a partnership-managed model must perform a financial spending analysis in accordance with TEA requirements. The financial spending analysis will provide critical information to inform contract negotiations with partner organizations, including data on current per pupil spending amounts for district schools and the costs of district-provided services to schools. School action providers can share information about technical assistance organizations that can assist districts in conducting this analysis. | Financial spending analysis
District completes required online learning modules or Leadership Academy program from the Texas Authorizer Leadership Academy (TALA) initiative | For districts implementing partner-managed models, the district must commit to participation in the Texas Authorizer Leadership Academy (TALA). TALA is a new, TEA sponsored charter authorizer support initiative to improve district authorizing practices and orient district leaders to replication and expansion strategies. TALA will offer training to school district leaders via competency-based online modules, and annual intensive leadership academy, and an annual summit conference, in addition to an authorizer framework and handbook. At a minimum, districts must complete the TALA online modules or the Leadership Academy. | Completion of TALA online modules or Leadership Academy
Year 1 - Planning Phase 3: Recruit for Call for Quality Schools - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for building a pipeline of partner organizations and school leaders | Based on selected school action(s), districts should develop a strategic plan for recruiting and/or developing partner organizations and school leaders. | Partner recruiting strategy summary document
Year 1 - Planning Phase 4: Authorize - Finalize plans for partnerships/new schools and execute contracts
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Release Call for Quality Schools (CQS) application and review process for school partners | RFP/application should solicit a comprehensive plan from partner organizations. At a minimum, plans should address the five levers of the Effective Schools Framework. For districts implementing a two-round CSQ process, this step represents the second round for soliciting final applications to operate partner schools. | CQS / application materials
District approves partner(s) or new schools for school action | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved partner application
Negotiate and approve contract terms and performance expectations for school partners and new school leaders | Negotiations to address: (1) school staffing model, (2) school funding model, (3) initial term length of agreement and renewal conditions, (4) facility agreement; (5) school operating autonomies, (6) performance expectations | Signed partner contracts
Year 1 - Planning Phase 5: Transition - Support transition planning for schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
School calendar and schedule | Partner determines school calendar and schedule | Partner board minutes
District services | District has given partner a list of services that are available for purchase and their respective prices | List of services
Budget autonomy | Partner organization has adopted budget for its schools | Partner board minutes
Partner school funding | Partner organization receives access to contracted funds in the amount and on the cadence agreed to in the contract | Partner organization verification
Staffing autonomy | Partner is able to hire and compensate school staff as it sees fit (in accordance with the contract) | Partner organization verification
Partner-district operating procedures | Partner and district have clear written operating procedures that address high-priority interfaces (e.g., finance, HR, discipline) | Partner organization verification
Year 2 - Implementation: District implements partnership with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School opens operated by partner organization
District and partner have agreed to a data reporting plan and cadence | District and partner organization establish date reporting plan that is aligned to partner contract and ensures timely reporting of leading and lagging indicators. | Data reporting plan
District implements in-district authorizing activities to monitor partner performance (as outlined in contract) | Authorizing activities defined by district authorizing policies and partner contracts; may include, but not be limited to: 1) Annual academic, financial, and organizational review of school performance; 2) Interim data reporting to track leading indicators of school performance; and 3) On-site, third-party school review visits during the first and subsequent years of school opening aligned to Texas Effective Schools Framework (ESF) levers. | Partner and/or district performance reports

## SA-New School, District Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-New School: District Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a new school campus. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Review and update (as necessary) district student enrollment policies for the new school | In addition to new school opening policies, district should consider if any "student enrollment policies" need adoption or revision to implement planned school actions. | - Student enrollment policies - Board meeting minutes for policy revisions/adoption (if applicable)
Year 1 - Planning Phase 3: Recruit - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for recruiting school leaders and/or organizations to plan and open new schools. | Districts should develop a strategic plan for recruiting individuals or organizations to plan and implement the new school. | School leader recruiting summary document
Year 1 - Planning Phase 4: Approve - Approve and finalize plans and performance agreements for new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Leaders participate in a new school design program and develop a plan for the new school | Leaders complete a rigorous new school design program that results in a new school design plan that includes but is not limited to the school's educational program, school culture, operations plan, and systems and structures for improvement. Plans should address the five levers of the Effective Schools Framework. | New school design plan
District superintendent and board approves plans for new school opening | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved new school design plan
Finalize performance expectations and district operating support for new schools. | As part of new school approval process, district should established performance agreement for the new school that establishes performance expectations, including enrollment targets for students that have attended or who are zoned to attend a Comprehensive or Targeted school. The performance agreement should also address plans for operational flexibilities (if applicable) that will be granted to the new school, and how the district will support and manage implementation of the educational model described in the new school's design plan. | School performance agreement
Year 1 - Planning Phase 5: Transition - Support transition planning for new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
Year 2 - Implementation: District implements new school with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
New school opens
New school meets student enrollment targets | Enrollment at a new school must prioritize students attending or zoned to a 2019–2020 Comprehensive and/or Targeted School. | Student enrollment data
New schools operates with appropriate autonomies | District is providing appropriate operating autonomies to new schools as defined by school performance agreement. | School performance agreement
School participates in formative school quality review process with third party technical assistance provider organization. | District partners with third party technical assistance provider organization to conduct a formative, on-site school review process aligned to the ESF framework. Review process provides formative feedback on school practices and alignment to new school academic model. | School review report

## SA-New School, Partner Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Partner Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a district authorizing policy. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Adopt district authorizing policies | District must adopt the TEA model authorizing policy if implementing partner-managed school models. In addition to authorizing policies, district should also consider if any "school choice policies" need adoption or revision to implement planned school actions. | District authorizing policy and board minutes
Conduct financial spending analysis in accordance with TEA requirements | LEAs pursuing a partnership-managed model must perform a financial spending analysis in accordance with TEA requirements. The financial spending analysis will provide critical information to inform contract negotiations with partner organizations, including data on current per pupil spending amounts for district schools and the costs of district-provided services to schools. School action providers can share information about technical assistance organizations that can assist districts in conducting this analysis. | Financial spending analysis
District completes required online learning modules or Leadership Academy program from the Texas Authorizer Leadership Academy (TALA) initiative | For districts implementing partner-managed models, the district must commit to participation in the Texas Authorizer Leadership Academy (TALA). TALA is a new, TEA sponsored charter authorizer support initiative to improve district authorizing practices and orient district leaders to replication and expansion strategies. TALA will offer training to school district leaders via competency-based online modules, and annual intensive leadership academy, and an annual summit conference, in addition to an authorizer framework and handbook. At a minimum, districts must complete the TALA online modules or the Leadership Academy. | Completion of TALA online modules or Leadership Academy
Year 1 - Planning Phase 3: Recruit for Call for Quality Schools - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for building a pipeline of partner organizations and school leaders | Based on selected school action(s), districts should develop a strategic plan for recruiting and/or developing partner organizations and school leaders. | Partner recruiting strategy summary document
Year 1 - Planning Phase 4: Authorize - Finalize plans for partnerships/new schools and execute contracts
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Release Call for Quality Schools (CQS) application and review process for school partners | RFP/application should solicit a comprehensive plan from partner organizations. At a minimum, plans should address the five levers of the Effective Schools Framework. For districts implementing a two-round CSQ process, this step represents the second round for soliciting final applications to operate partner schools. | CQS / application materials
District approves partner(s) or new schools for school action | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved partner application
Negotiate and approve contract terms and performance expectations for school partners and new school leaders | Negotiations to address: (1) school staffing model, (2) school funding model, (3) initial term length of agreement and renewal conditions, (4) facility agreement; (5) school operating autonomies, (6) performance expectations | Signed partner contracts
Year 1 - Planning Phase 5: Transition - Support transition planning for schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
School calendar and schedule | Partner determines school calendar and schedule | Partner board minutes
District services | District has given partner a list of services that are available for purchase and their respective prices | List of services
Budget autonomy | Partner organization has adopted budget for its schools | Partner board minutes
Partner school funding | Partner organization receives access to contracted funds in the amount and on the cadence agreed to in the contract | Partner organization verification
Staffing autonomy | Partner is able to hire and compensate school staff as it sees fit (in accordance with the contract) | Partner organization verification
Partner-district operating procedures | Partner and district have clear written operating procedures that address high-priority interfaces (e.g., finance, HR, discipline) | Partner organization verification
Year 2 - Implementation: District implements partnership with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School opens operated by partner organization
District and partner have agreed to a data reporting plan and cadence | District and partner organization establish date reporting plan that is aligned to partner contract and ensures timely reporting of leading and lagging indicators. | Data reporting plan
District implements in-district authorizing activities to monitor partner performance (as outlined in contract) | Authorizing activities defined by district authorizing policies and partner contracts; may include, but not be limited to: 1) Annual academic, financial, and organizational review of school performance; 2) Interim data reporting to track leading indicators of school performance; and 3) On-site, third-party school review visits during the first and subsequent years of school opening aligned to Texas Effective Schools Framework (ESF) levers. | Partner and/or district performance reports