## Turnaround Foundations
Campus Turnaround Plan
Campus Information
District Name: |  |  | Superintendent: | DCSI: | Board President:
Texas ISD |  |  | Lizette Ridgeway | Nicole Seltman | Garrett Black
Campus Name: |  |  | Campus Number: | Principal: | Principal Supervisor:
TEA Academy |  |  | 123 456 789 | Jessica McLoughlin | Tim Regal
School Year Plan was Developed: |  |  | ESF Diagnostic Date: | ESF Facilitator: | Date of Board Approval:
2019 |  |  | 2020-10-07 | Lindsay Denman | 2020-02-07
Turnaround Method
Select the turnaround method your campus is pursuing. See the Description of Methods guidance document for more information.
Method |  | Description |  |  |  | Check one
School Improvement |  | Improve foundational practices at the campus by working with a vetted improvement program and/or developing an internal capacity building plan.
School Action-Reassign |  | Close the low-performing campus and reassign students to higher performing (A or B rated) campuses or new campuses.
School Action-Restart: District Managed |  | Restart a school by implementing the Accelerating Campus Excellence model or ACE-like model (including Accelerating Campus Excellence (ACE) turnaround plans).
School Action-Restart: Partner Managed |  | Restart a school with a Texas Partnership with an existing operator with a track record of success
School Action-New School: District-Managed |  | Create or phase in a new school managed by the district at a new or existing facility
School Action-New School: Partner Managed |  | Create or phase in a new school with a Texas Partnership at a new or existing facility
Outcomes
For each essential action, describe the current implementation level on the campus (using the ESF Diagnostic Summary Report) and what full implementation will look like on this campus. Reference the Key Practices in the Effective Schools Framework to develop the vision. Campuses should strive to be at or near full implementation within two years after implementing this Turnaround Plan for two years.
1.1 Develop campus instructional leaders with clear roles and responsibilities. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | We currently have a roles and responsibilities document for all members of our ILT. Additionally, we have identified which teacher is supervised by which administrator. We are implementing T-PESS for Administration evaluation (this was implemented by the district). Additionally, ILT members have expectations around walkthroughs and observations. The ILT meets each week and uses an agenda that covers a variety of topics including: CIP review, discipline data, and campus business. At this time, the ILT does not spend time consistently discussing instructional rounds, walkthrough or observation data. While the campus principal does meet with members of ILT weekly, there is not a strong system for observations/feedback cycles for ILT members to practice their skills. There is a need at the campus to develop the leadership of ILT members and teacher leaders as well. Additionally, while ILT members have goals- there is no evidence that they continually compare themselves to these goals or adjust course to meet the goals.
Partial Implementation
Prioritized Focus Area from ESF Diagnostic?
Yes
Full Implementation: Vision
At full implementation, we will have an updated document reflecting the roles and responsibilities for all ILT members. This will include the teachers each member supervises. The ILT will have clear expectations to align their calendars to the observation/feedback cycles for each teacher- which will occur at least 1x per month (but vary based on need/student data). PLCs and key trainings, staff meetings, etc. will be placed on a year-long calendar and distributed to all staff at the start of each year. The ILT will meet on a recurring basis and follow a set agenda that will include student data analysis and next steps as part of each meeting. ILT members will meet with teachers they manage/supervise at the start of the year to review goals and performance expectations. Teachers and ILT team members will have a clear understanding of their individual goals and will be able to discuss progress toward goals throughout the year. We will check in on progress of ILT goals at MOY and, again, formally at EOY. ILT members will have a running record of the feedback and action steps they have shared with their teachers. We will have a strong pipeline of Teacher leaders (who will lead our PLC meetings) and be involved in monthly school-wide larger leadership team meetings. These teacher leaders will facilitate high-quality PLC meetings aligned to data-driven instruction, instructional best practices and/or lesson plan creation and rehearsal. We will have a record of all agendas and notes from PLC meetings. As a result of these actions, teachers and leaders will report greater clarity on their roles and responsibilities and a greater understanding of their goals and progress toward their goals throughout the year. Additionally, PLCs will be seen as useful meetings that develop our teachers and support student achievement. Additionally, there will be a robust campus handbook in place including all campus procedures and policies, especially those around roles and responsibilities, and teacher and leadership team evaluation processes.
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | We aim to recruit and attract teachers with elementary and middle school experience. We attend job fairs fairly consistently. However, we do not currently have strong marketing or recruitment strategies at the campus or district level. Our hiring criteria is based on years of experience, content knowledge, and alignment to mission and values; however, we need to incorporate that into the selection process in a more formal way. We include principal, ILT, and teachers on the hiring committee for candidates. It is suggested that we include a sample teach as part of our interview process. We use summer PD and PLCs to look at past data, set goals, and spend time learning how to deconstruct standards and create learning objectives. We also set aside additional PLC time for new teachers. We place teachers in roles based on preference, content knowledge and student need. We aim to make assignments based on student data in the future and strive to put our most effective teachers in the most high-needs courses, when appropriate. We evaluate teachers using T-TESS and look for opportunities to give high-performing teachers leadership roles (PLC leads). We have not created consistent systems or practices to support struggling teachers. There is not yet a shared vision of what excellent teaching looks like at our school; and, we need to work on securing a consistent pool of preferred substitutes for our campus.
Beginning Implementation
Prioritized Focus Area from ESF Diagnostic?
No
Full Implementation: Vision
At full implementation, our district will work hand in hand with our campus to ensure we have a robust recruitment strategy in place including: attending college and teacher fairs, and hosting an internal referral campaign. Additionally, we will work with our HR team to track our candidates and determine which efforts result in the best production of high-quality candidates. At the school level, we will have a more aligned selection process including a sample teach lesson, a teacher panel, and formal interview. We will align our interview questions to assess for content knowledge, AND culture fit around our mission/vision/values. We will add in several role plays as well. Each year we will use student data, as well as other factors (content knowledge, team diversity and experience) to place teachers in the best fit positions. We will identify our top performing teachers as an ILT. We will also strive to offer differentiated, personal learning opportunities for our staff as a retention strategy. We will assign different members of the ILT to each cohort (new teachers, proficient teachers, teacher leaders). We will place teacher leaders in other leadership roles (Grade-level chair, committee chairs, etc. ) in order to build their adult leadership skills and recognize them for their success. We will provide ongoing support and training for our teacher leaders. Lastly, we will create a substitute committee to help foster positive relationships with some of our best substitutes and to cultivate them for potential long-term positions as they become available.
3.1 Compelling and aligned vision, mission, goals, values focused on a safe environment and high expectations. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | There are artifacts in classrooms, hallways, and shared spaces that reflect our campus expectations, rewards systems, and character education. However, staff members are not able to name the campus mission and vision. There is some shared understanding of campus implied values - reducing student referrals, increasing student engagement, implementing consistent behavior expectations. We do have systems in place to ensure students are monitored at less structured times such as arrival, dismissal, lunchtime, etc. We administer annual surveys to staff, students, and parents and well as informal surveys throughout the year. At this time, we haven't yet developed clear systems to share interim survey data with campus staff. Overall, there is a need to make the campus mission, vision, and values more explicit and shared among our school community.
Partial Implementation
Prioritized Focus Area from ESF Diagnostic?
No
Full Implementation: Vision
At full implementation, we will have engaged in a revision of our school mission, vision, and values that involves the school staff, students, and community in refining these essential components of our school. Our mission, vision, and values will be prominently displayed in classrooms, shared spaces, and school areas. All staff, students, and families will be able to speak to the mission, vision, and values. We will have established both student/family and staff handbooks that guide our behavior. Staff and students will interact with one another in a respectful way at all times. All staff will know the expectations for ALL students and hold students to these expectations at all times. Our staff and students will feel comfortable holding one another accountable for meeting expectations. We will start each year with strong monitoring of students in shared spaces and set the tone early on regarding expectations during less structured times: lunch, recess, arrival, dismissal, etc. We will use a culture rubric during walkthroughs during these periods to obtain ongoing data that will be analyzed by the larger leadership team to make adjustments and refinements. We will have students create hallway and bathroom visuals that remind one another of the shared expectations. Classrooms will also have the same expectations posted across the school. We will continue our practice of surveys, ensure we are analyzing the interim surveys with our staff, and sharing the survey data with our staff, students, and school community. Our campus will feel positive and inclusive; and, expectations will be held high for our staff and students.
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | We have a YAG that includes the # of days in each unit, what readiness/supporting TEKS are addressed, and when the assessments are administered. The YAG is organized for each content area. However, the YAG does not currently allow for re-teaching or re-assessing. Teachers need to find the time during Do Nows, small group, etc. We do have dedicated RtI time for math and ELAR . The dates for our Interim Assessments are on our year-long calendar and we have the Interim Assessments and benchmarks calendared throughout the year. We use sample STAAR questions and other similar questions to build our assessments (common assessments).We use the B.I.G. 8 Correlation chart to define high-yield strategies. Teachers also use an Instructional Focus document that helps identify vocabulary, TEKS, ELPs, misconceptions, and what resources are available. There is evidence of modifications and accommodations being used across classrooms in the school as well as anchor charts, content-rich texts, etc. PLCs are used (as well as content planning days) to provide ongoing training and support of instructional materials.
Partial Implementation
Prioritized Focus Area from ESF Diagnostic?
No
Full Implementation: Vision
At full implementation, we will have a refined Scope and Sequence for each core content area that not only includes units aligned to TEKS, but it will also include all assessment dates and dedicated time for re-teach after each interim assessment. Each core content subject will be provided with instructional materials for each unit that includes essential questions, key ideas, suggested resources and texts, and examples of classroom materials (anchor charts, graphic organizers, etc.) that will support their learners. We will provide common assessments (aligned to the rigor of STAAR) administered at least 3x a year for all STAAR tested courses. These assessments will include STAAR released questions, as well as other questions that are aligned to the level of rigor of STAAR. We will track mastery on each assessment, and share this information with teachers, students, and families. We will provide our teachers with ongoing professional development aligned to best practices in terms of instructional materials, resources, and strategies. Teachers will be provided resources to support their English-Learner students as well as students with disabilities. Our Special Education team will be a part of weekly PLCs and meetings when looking at student work and data. Our campus-wide calendar will allow for quarterly content planning days for each department(and our special education teachers as well) - during which they will internalize the upcoming units and materials provided. We will provide ongoing training to our staff, especially in terms of strategies for English-Learners, students with disabilities, and other relevant content as the needs arise.
5.1 Objective-driven daily lesson plans with formative assessments. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | We use the district lesson plan template which includes content objective, TEKS, language objective, ELP, differentiation, strategies, essential questions, anticipated misconceptions, as well as instructional procedures such as: check for understanding, Activating Prior Knowledge, Guided Practice, Independent Practice, and lesson closing. Lessons plans are aligned to our curriculum scope and sequence with a daily objective that is aligned to the standard. Each classroom posts the daily objectives and teachers reference it at the start of each lesson. Most teaching teams divide up lesson planning responsibilities and use PLCs or content planning days to plan lessons. Teachers report that they use backwards-planning to plan lessons. Some teachers share they modify team-created plans to meet the needs of their students. At this point, teachers are not creating exemplar student responses for their lessons. Teachers use Google Drive to store plans so the ILT can access them. Lessons plans are expected to be submitted 2 weeks in advance. However, there is no set protocol or process for feedback on plans. Some teachers may receive feedback on plans from their coaches.
Beginning Implementation
Prioritized Focus Area from ESF Diagnostic?
Yes
Full Implementation: Vision
At full implementation, we would want all teams submitting weekly lesson plans on the Monday morning, one week in advance. These lesson plans would include clear student friendly content objectives as well as language objectives. The lesson plans would be written on a shared lesson plan template with openings, closings, and objective-driven activities (Introduction to New Material, Guided Practice, and Independent Practice). Lesson plans would also include sections to include differentiation. Most importantly each lesson would be submitted with a formative assessment, teacher exemplar, and student exemplar. The lesson plans would align to our current YAG and scope and sequence. The lessons will be based on gathering and responding to student data and include several checks for understanding throughout the lessons. We would want to be able to check for fidelity of execution to the lesson plan during our classroom observations. Each lesson plan would be reviewed by a member of the ILT on Monday/Tuesday the week BEFORE it is taught. Teachers would receive 1-5 pieces of actionable feedback aligned to the plan. The ILT will be calibrated and normed on the feedback provided to teachers. Lastly, there will be a clear process in place for teachers to make changes to their plans and submit final versions by the Friday the week before the lesson is taught.
5.3 Data-driven instruction. | Current Implementation: Summary
| Implementation Level At Diagnostic |  | We spent time this summer reflecting on STAAR data, deconstructing the TEKS, and reviewing the YAG. The TEKS deconstruction document is used to plan for instruction. We have monthly RtI meetings to review RtI binders and student data. Data meetings are held after assessments (usually within one week). Teachers and leaders are familiar with using item-level analysis to prioritize re-teach and enrichment lessons. Our data meetings currently do not involve creating teacher or student exemplars. We also do not plan for re-teach or practice any re-teach lessons. There is confusion around the need for (and the expectations for) student data folders across the campus.
Beginning Implementation
Prioritized Focus Area from ESF Diagnostic?
Yes
Full Implementation: Vision
At full implementation, our campus will be data-driven in all aspects. We will have dedicated time after each interim assessment to review data as a leadership team and to create action plans based on the data that include re-teaching for skills/standards/students that have not yet shown mastery. We will use data and student performance to guide our decisions regarding observations, professional development, PLC topics, and teacher placement. We will have weekly data meetings where teachers are able to meet in teams, with a member of the ILT, and analyze their most recent data (whether it be from an exit ticket, unit test, or more summative form of data). These data meetings will be run by ILT members who have had training on WDMs and who will receive ongoing observation and coaching from the Principal. The WDMs will allow teachers to analyze data, identify the misconceptions, and plan for effective re-teach. The ILT will observe re-teach instruction as needed to provide ongoing support and coaching. Each week, we will review the re-teach and re-assessment data to determine next steps. Classrooms will track their class-wide Interim Assessment (IA) data; we will have a school-wide bulletin board that shows the IA data for all subjects at our school and the progress after each IA. We will celebrate students who made the most growth on their IAs, as well as those who have achieved the "Meets" or "Masters" bar at each administration in a school-wide assembly. In order to ensure all these systems are able to occur on a consistent basis, we will need to be intentional about our master schedule and protect time for weekly data meetings, leadership team data analysis meetings, time to re-teach, and re-assess.

## dropdowns (hidden)
Impl level | Yes | EA nums
Full Implementation | No | 1.1
Partial Implementation |  | 2.1
Beginning Implementation |  | 3.1
Planning for Implementation |  | 4.1
Not Yet Started |  | 5.1
5.3
|  |  | Essential Action | Pre-Implementation | Implementation Year 1 | Implementation Year 2 | Implementation Year 3 and beyond
1.1 Develop campus instructional leaders with clear roles and responsibilities.
2.1 Recruit, select, assign, induct and retain a full staff of highly qualified educators.
3.1 Compelling and aligned vision, mission, goals, values focused on a safe environment and high expectations.
4.1 Curriculum and assessments aligned to TEKS with a year-long scope and sequence.
5.1 Objective-driven daily lesson plans with formative assessments.
5.3 Data-driven instruction.
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These milestones must be included in the campus' current year TIP, Cycle 4
Note on Q17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Milestones in this column can be focused on sustainalibyt of systems implemented in years 1 and 2 of implementation. A campus that is ordered to implement a turnaround plan may modify the milestones in this column once they receive two consecutive acceptable ratings.

## School Improvement
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Improvement Turnaround Plan
District Commitment Theory of Action
In this section, describe the District Theory of Action and the District Commitments that will support the campus' essential actions found in the plan. The District Theory Commitment Theory of Action should address each of the Foundational Essential Actions and DDI.
If the district provides ongoing support and coaching of the campus leader in terms of the foundational Essential Actions, especially 5.1 and 5.3, and works with the principal and leadership team to protect their time in a way that aligns to instructional leadership roles and responsibilities, and supports the campus with attending and actively engaging in the capacity building cohorts, while also working with the campus to allow for sufficient control with the hiring process, as well as partnering with the curriculum division to ensure they are able to provide the campus with the necessary tools and resources for curriculum and instruction, then the campus will be able to further clarify the roles and responsibilities of their leaders, drive toward creating a more data-driven school culture and ensure teachers are using high-quality lesson plans aligned to student learning objectives. They will be able to establish a strong school culture with aligned mission, vision and values.
System and Capacity Building
In this section, describe the efforts the campus and district will make to build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe areas in which you will build systems, skills, and capacity in district and campus staff. |  | What potential program or partners will the campus/district work with in this area? |  | When will this be a focus? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
We aim to build capacity in all our STAAR tested courses, grades, and teachers this year around DDI. This will includes training teachers and leaders on DDI processes and incorporating strong, weekly data meetings into our practice. We will also include structures and time to allow for re-teaching and re-assessing. Lastly, we will ensure we give at least 3 Interim Assessments in each STAAR-tested course that are aligned to the rigor of the State Assessment. |  | ESC 21- TIL Cohort - DDI |  | 2020 | Year 1: The TIL cohort combines in person PD, face to face learning and coaching and ongoing support from our ESC. We will participate in the cohort and work with our ESC to implement DDI practices in our school. We will meet with the cohort 3 times during the year. Additionally, we will have ESC visits to our campus and ongoing coaching on our DDI practices. We will use our reflections on these practices to problem-solve and improve our DDI Implementation at the campus. | 5.3, 4.1
We aim to create clear roles and responsibilities for all members of the leadership team. Additionally, we aim to provide greater clarity to ILT members in how to lead their departments/grade-levels. We want to improve the structure of our weekly ILT meetings to ensure we are focused on student and teacher data. |  | External Capacity Builder- New Leaders |  | 2020 | Year 1: The New Leaders cohort includes a combination of face to face PD, ongoing one on one coaching, and implementation support at the campus. We plan to attend the cohort this coming summer to begin to work on clearly defining the roles and responsibilities of all campus leaders (beyond the principal and ILT). The focus is to build capacity across our campus. The Principal will receive on going support and coaching in this work. Additionally, there are several intersessions the ILT will attend. | 1.1, 2.1, 5.1
This year, we want to ensure we have strong systems in place for regular feedback on our teachers' lesson plans. We plan to create strong protocols to allow this to happen consistently so that our teachers receive meaningful feedback on their plans that results in stronger plans and stronger student outcomes. |  | Internal Capacity Building Efforts |  | 2020 | Year 1: We will partner with our district and other campuses that have created similar protocols with success. The Principal supervisor will support the ILT in creating the new processes and protocols and helping to manage the change with this new system. The Principal supervisor will provide ongoing coaching and support to the Principal and ILT in this practice. | 5.1
Our district curriculum department will work collaboratively with TEA Academy to provide Scope and Sequences for each core content area that are aligned to the TEKS. We will ensure that each core content subject has the necessary instructional materials that will support student achievement. Our district has committed to providing 3 IAs per content area that align to the rigor of STAAR. We will support the curriculum department by identifying teachers who can support these efforts as needed. The Principal supervisor will support our ILT in helping to refine the instructional materials we provide to our teachers, including unit plans, YAG, resources, etc. |  | Internal Capacity Building Efforts |  | 2021 | Focus in year 2: We will begin this work in the summer of 2020 as we work to identify teacher leaders who can work with the curriculum department to modify/adjust scope and sequences and work to create common assessments. We will provide ongoing support by providing our teacher leaders engaged in this work the time to work on this at least 1x per quarter. We will provide ongoing opportunities for our staff to provide feedback on the materials and resources. We will observe implementation of materials on an ongoing basis. Additionally, we will provide the time in our scope and sequence for assessing, re-teaching, and re-assessing as needed. | 4.1
We aim to partner with ESC 21 and join their TIL cohort on Student Culture and Routines. We want to train our ILT and teacher leaders on establishing strong routines that demonstrate high expectations across our campus. Our intent is to really strengthen and define the routines in shared spaces at key parts of the day - arrival, dismissal, recess, transitions, lunch, etc. The TIL Cohort will support us in the planning and roll out of these routines. |  | ESC 21 TIL Cohort- Student Culture and Routines |  | 2021 | Focus in Year 2:The TIL cohort combines in person PD, face to face learning and coaching, and ongoing support from our ESC. We will participate in the cohort and work with our ESC over the summer to create routines and procedures for our school. We will introduce these back at the campus and focus on implementing these routines in summer PD, so that our teachers are ready to roll these routines out during the first few weeks of school. We will meet with the cohort 3 times during the year. Additionally, we will have ESC visits to our campus and receive ongoing coaching and feedback on student culture at TEA Academy. We will use our reflections on these practices to problem-solve and improve our culture throughout the year. | 3.1
We aim to create more staff involvement in a refined approach to hiring and retaining the best teachers. We would like to build capacity in this area, by creating a teacher hiring committee who will help refine and execute the new, revised hiring efforts. This includes attending job fairs, helping modify the interview selection process, and participating in interviews for candidates. We aim to have different cohorts for professional development for our teachers and create individual ILT members to lead each cohort (new teachers, advanced teachers, teacher leaders). Our substitute committee will be tasked with identifying high-performing substitutes and building positive relationships with them. |  | Internal Capacity Building Efforts |  | 2021 | Focus in year 2: We will do most of this work internally. It will start by identifying those interested in being on our committees (hiring, substitute, etc.). The ILT will ensure we have time on our year long calendar to meet with our committees, plan, and gather feedback on the processes. We will create different year-long PD opportunities and calendars for our different cohorts of teachers. We will ensure we have at least quarterly touchpoints with HR to evaluate our processes and the changes we have made. | 2.1
Critical Implementation Milestones
In this section, describe the critical implementation milestones (high-level description of actions that will be completed) that the campus and/or district will meet in each year of implementation in order to achieve the vision of full implementation of each Essential Action shared on the Turnaround Foundations tab. Milestones for the 2-3 high leverage focus areas identified in the ESF Diagnostic must be addressed first, as these are the campus' largest gaps in practice and systems (and will have the greatest impact on the implementation of other Essential Actions). The milestones listed here must be included in each year's Targeted Improvement Plan. Add rows as needed.
Pre-Implementation | [5 empty] | Essential Action
Ensure budget and calendar allow for TIL cohort participation for all ILT Team Members | [5 empty] | 5.3
Share focus areas and major initiatives with staff at end of summer | [5 empty] | 1.1
Begin process for creating next year's master calendar with protected time for meetings, assessments, data analysis, and re-teaching | [5 empty] | 5.3
Plan summer PD calendar with ample time to address focus on DDI and lesson planning | [5 empty] | 5.3
Implementation Year 1 | [5 empty] | Essential Action
ILT facilitates effective weekly data meetings where teachers are able to participate in the process of analyzing data, identifying misconceptions, and planning strong re-teach plans which in turn lead to improved student outcomes | [5 empty] | 5.3
ILT and teacher leader behaviors and actions are grounded in clear roles and responsibilities with a focus on instructional leadership | [5 empty] | 1.1
Teachers participate in meaningful professional development opportunities throughout the year that align to the campus focus areas and result in stronger outcomes for students | [5 empty] | 1.1
Teachers are consistently receiving meaningful feedback on their lesson plans within designated timelines that result in stronger student achievement outcomes | [5 empty] | 5.1
Implementation Year 2 | [5 empty] | Essential Action
Our robust hiring process employs multiple high-leverage processes for recruiting and hiring strong candidates who demonstrate content knowledge as well as an alignment to our school mission, vision and values | [5 empty] | 2.1
Our teachers receive differentiated professional development aligned to their individual learning goals and needs | [5 empty] | 2.1
Our school's mission, vision, and values are apparent throughout our school and community. Our staff, students, and families can speak to our mission, vision, and values and are deeply connected to our school | [5 empty] | 3.1
Our school culture demonstrates a commitment to high-expectations for all students, staff, and families | [5 empty] | 3.1
Teachers for STAAR tested courses are provided with high quality curricular materials that support the achievement of all students including: scope and sequence, unit plans, text resources and other instructional materials | [5 empty] | 4.1
Implementation Year 3 and beyond | [5 empty] | Essential Action
Milestones in this column can be focused on sustainability of systems implemented in years 1 and 2 of implementation. A campus that is ordered to implement a turnaround plan may modify the milestones in this section once they receive two consecutive acceptable ratings.
Our campus has processes in place to observe, monitor, and adjust our practices as they relate to DDI. We review student achievement data, teacher survey data, and observational data to adjust course and continue strengthening our weekly data meetings as well as our interim assessment data analysis processes | [5 empty] | 5.3
Our campus has processes in place to audit, monitor, and adjust our practices as they relate to protecting ILT time and clarifying roles/responsibilities for ILT and teacher leaders. We intentionally build the capacity of teacher leaders and have a pipeline in place for additional leaders on our campus. Our campus leaders prioritize instructional leadership including action coaching, data analysis and team leadership | [5 empty] | 1.1
Teachers continue to receive high-quality feedback on lesson plans with ample time to respond to the feedback and adjust their plans so that the lessons we present to our students are objective-driven and aligned or the TEKS | [5 empty] | 5.1
Our campus continues to gather data on our student culture and routines. We adjust our focus areas and build out new routines/revise existing routines for the start of the next year based upon this data and our culture walkthrough observations | [5 empty] | 3.1
Our campus partners with HR in meaningful ways to support the hiring and retention of highly effective teachers | [5 empty] | 2.1
Our campus partners with the curriculum development to ensure our curricular materials provided to our staff are high-quality, useful, and produce strong student outcomes | [5 empty] | 4.1
Budget and Financial Resources
Funds outlined in the budget table should include any supplemental costs required to implement the turnaround plan for 2 or more years. For example, salaries for teachers and principals should not be included; however, if the initiative calls for teacher stipends to cover extra duties, those costs should be accounted for in the table.
Category | Amount |  | Description
Payroll | 10000 |  | Stipends for Teacher Committees (hiring, curriculum, substitute) across two years
Professional Development | 80000 |  | DDI, Student Culture and New Leaders Coaching Costs
Supplies and Materials | 5000 |  | Vision, Mission, Values materials
Other Operating Costs | 0 |  | N/A
Capital Outlay | 0 |  | N/A

## School Action (SA)-Reassign
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Reassign
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. |  | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on the school reassignment plan. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop and finalize plans for student reassignment
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Establish school selection and enrollment process for student reassignment, including identification of target schools for student placement | District should establish a school assignment/selection and enrollment process for reassigned students that maximize opportunities for students and families to enroll in high-quality, best-fit schools. | - Summary of student reassignment/ enrollment process - List of target schools with information about performance levels and enrollment capacity
Develop and implement a strategy for supporting families with decision making support for student enrollment / reassignment. | Strategy should ensure that every family has access to information and case management support to evaluate options and make informed decisions about school reassignment/enrollment. | Summary of student enrollment support services
Establish plan for use of closed school facility (or process for determining the plan) | District should develop and clearly communicate short- and long-term plans for future use of the closed school facility. | External communication of facility plans
Year 1 - Planning Phase 3: Approve and finalize plans and goals for student reassignment to new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Finalize goals for student reassignment process | Reassignment process should include specific goals for evaluating success; including measures to determine number and/or percentage of reassigned students that enroll in higher-performing campuses. |  | Goals included in board approved reassignment plan
District superintendent and board approves plans and policies for student reassignment process | Board approves reassignment plan and adopts new district enrollment policies (as necessary) to support plan implementation. |  | Board meeting minutes
Year 1 - Planning Phase 4: Transition - Support transition planning for students and schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Develop and Implement a detailed implementation plan for the reassignment process | Detailed Implementation plan should address a comprehensive set of activities to support the reassignment of students to new campuses, as well as activities to support the smooth transition of the closing facility/campus. |  | Reassignment implementation plan
Year 2 - Implementation: District implements reassignment with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence |  | Start Date | End Date | Notes
Students attend new schools and school is closed
District implements reassignment implementation plan | Detailed Implementation plan should include activities during the transition school year to ensure all students are served in campus at school district |  | Reassignment implementation plan
Schools attended by students participate in formative school quality review process with third party technical assistance provider organization. | District partners with third party technical assistance provider organization to conduct a formative, on-site school review process aligned to the ESF framework. Review process provides formative feedback on school practices and alignment to new school academic model. |  | School review report

## SA-Restart, District Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Turnaround Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning and Implementation Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align restart strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Identify Project Teams and Committees | ACE Design Team / Project Lead – there must be a person(s) identified as project lead, with the authority (either by existing role or Superintendent designee) to make decisions and the C-level relationships to ensure the process moves at the appropriate speed. Most important departments in the planning/design phase include: Human Capital, School Leadership, Communications, Operations/Finance | - District project manager - Document that outlines district committee that will lead the work
Establish school program requirements | This will follow the five core pillars of the ACE model: (1) Strategic Staffing, (2) Instructional Excellence, (3) Extended Day, (4) Social and Emotion Learning, and (5) Community and Parent Partnerships. | One-pager on programmatic elements by ACE pillar; ongoing assessment of district's ACE implementation plans
Identify third-party implementation partner | Describe the third-party implementation partner that the district proposes to partner with or is partnering with. Describe the experience this partner has in supporting other campuses with the design and implementation of the specific ACE turnaround model. Describe, specifically, the activities that the partner will support the campus with. | Contract or MOU with third-party implementation provider
Year 1 - Planning Phase 2: Develop - Develop policies and systems for implementing ACE
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop campus administrator selection process | Districts should conduct a quantitative and qualitative analysis of current principals based on relative school performance vs. expected school performance. District leadership will be critical in helping to identify current leaders in the district that embody essential principal character traits. While many districts have a selection process outlined for the role of campus principal, districts may wish to use a condensed or modified selection process, in consideration that this will be a principal re-assignment and not an employee newly promoted to the principal role. The traditional process may also be condensed to ensure confidentiality prior to the broader announcement to the district and staff about the upcoming changes. | Administrator requirement blueprint
Develop Teacher Hiring/Selection Process | The teacher hiring process should begin with a quantitative and qualitative analysis of teacher performance across all teachers in the district. With this insight on performance, the newly selected campus principal will now have a target list for recruiting and assembling a team for the new campus. A principal will need to consider the composition not only of the overall teaching staff, but also within teams/depts/grade levels. | One-pager on programmatic elements by ACE pillar; ongoing assessment of district's ACE implementation plans
Develop principal and employee compensation structure. | Provide a detailed narrative description of the employment and compensation structure of the principal that details the principal's incentive payment and the assurance that the principal will continue to receive incentive payments over the next three years of implementation. Provide a detailed description of the employment and compensation structure of the teachers on the campus that details teacher incentive payments and the assurance that teachers will continue to receive incentive payments over the next three years of implementation. | Draft line-item ACE campus budget
Create a comprehensive budget plan | Districts will develop a line-item budget, including but not limited to, educator stipends, cost of extended day (transportation and enrichment programming), professional development, and social/emotional learning curriculum. | Draft line-item ACE campus budget
Develop an overall communication plan and strategy | A successful design and rollout of the ACE initiative with strong community and stakeholder support is contingent upon a district's ability to communicate effectively about the initiative. The communication plan should communicate key messages about why ACE is being implemented, who it impacts, and how it will be implemented. Districts should complete in the fall and early winter, so that materials are ready when official announcements begin. | Strategic Communication Plan
Year 1 - Planning Phase 3: Transition - Support transition planning for ACE model implementation
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Implement principal selection process | Select principal based on established recruiting/selection process. District should provide a narrative description of the principal's qualifications and why the district selected the principal to lead the ACE turnaround plan and the quantitative evidence that the principal has a demonstrated history of improvement in student academic growth at the campuses the principal has led or been a part of the management team at. | - Principal selected - Principal selection criteria document to outline selection process, rationale for selection, and principal resume
Implement principal contract with specific academic achievement improvements | District should execute a clear contract that contains the specific expected academic achievement improvements in each of the next three school years. | -Principal contract with detailed academic achievement improvements over the next three years
Implement teacher recruitment/hiring process | Hire teachers based on established recruiting/selection process. Provide a teacher roster by grade level, indicating which district the taught at in the preceding year. Provide evidence that at least 60 percent of the teachers on the roster had demonstrated instructional effectiveness during the previous school year. | Teacher hiring tracker
Identify data driven instructional practices | Describe the data-driven instructional practices to be implemented on the campus. Clearly link these practices to the specific actions within the Effective Schools Framework. | School design plan
Identify the system of observation and feedback for classroom teachers | Describe the system of observation and feedback for classroom teachers that will be implemented on the campus. Clearly link these practices to the specific actions of the Effective Schools Framework. | School design plan
Identify the curriculum for the school | Describe the curriculum that will be used at each grade level, how that curriculum was selected, and how teachers will be professionally developed to implement the curriculum. | School design plan
Identify the systems and practices to develop a positive school culture | Describe the systems and practices that the campus will implement to develop a positive school culture. Clearly link these practices to the specific actions of the Effective Schools Framework. | School design plan
Identify the systems and practices to ensure highly engaged families and communities | Describe the systems and practices that the campus will implement, including specific partnerships with specific parent and community groups, to ensure highly engaged families and communities. | School design plan
Identify extended learning opportunities | Describe the specific extended learning opportunities that will be afforded to students and how those students will be informed of those opportunities. | School design plan
Identify student services provided before and/or after school | Describe how the campus will provide student services before or after school. Describe, in detail, what services will be provided. | School design plan
Establish systems and capacity for formative, Effective Schools Framework-aligned progress monitoring during implementation year(s) | During the school year, the district will work with a third-party provider organization to conduct formative school visits to evaluate ACE model implementation and ESF-aligned school practices. School performance data will be tracked on either a 3-week or 6-week interim, depending on district processes, and will be compared where available, to 2018-2019 baseline data: (1) Student and staff attendance, (2) occurrences of discipline referrals, by sub population, and (3) academic interim assessments, in both K-2 and 3-8. | Progress Monitoring Plan
Year 2 - Implementation: ACE Implementation Fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School begins new school year as ACE campus
Establish afterschool enrichment opportunities for all interested students free of charge | These opportunities need to be open to all students, free of charge, and not solely University Scholastic League (UIL) activities. | Principal/District shared list of approved providers
Ensure transportation services | Ensure transportation services are in place for pickup after extended hour of instruction (typically around 4pm), as well as afterschool enrichment time (typically around 6pm). | Bus schedules and routes
Submit federal Afterschool Meals provider application for approval | Federal Afterschool Meals program allows eligible campuses to serve dinner and be reimbursed for those expenses. | Federal approval status
Complete parent / community engagement plan | Create schedule for PTA meetings/locations and determine adult basic education (ABE) and volunteer opportunities for parents and community members | Flyers, schedules, etc.

## SA-Restart, Partner Mangaged
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Partner Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a district authorizing policy. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Adopt district authorizing policies | District must adopt the TEA model authorizing policy if implementing partner-managed school models. In addition to authorizing policies, district should also consider if any "school choice policies" need adoption or revision to implement planned school actions. | District authorizing policy and board minutes
Conduct financial spending analysis in accordance with TEA requirements | LEAs pursuing a partnership-managed model must perform a financial spending analysis in accordance with TEA requirements. The financial spending analysis will provide critical information to inform contract negotiations with partner organizations, including data on current per pupil spending amounts for district schools and the costs of district-provided services to schools. School action providers can share information about technical assistance organizations that can assist districts in conducting this analysis. | Financial spending analysis
District completes required online learning modules or Leadership Academy program from the Texas Authorizer Leadership Academy (TALA) initiative | For districts implementing partner-managed models, the district must commit to participation in the Texas Authorizer Leadership Academy (TALA). TALA is a new, TEA sponsored charter authorizer support initiative to improve district authorizing practices and orient district leaders to replication and expansion strategies. TALA will offer training to school district leaders via competency-based online modules, and annual intensive leadership academy, and an annual summit conference, in addition to an authorizer framework and handbook. At a minimum, districts must complete the TALA online modules or the Leadership Academy. | Completion of TALA online modules or Leadership Academy
Year 1 - Planning Phase 3: Recruit for Call for Quality Schools - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for building a pipeline of partner organizations and school leaders | Based on selected school action(s), districts should develop a strategic plan for recruiting and/or developing partner organizations and school leaders. | Partner recruiting strategy summary document
Year 1 - Planning Phase 4: Authorize - Finalize plans for partnerships/new schools and execute contracts
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Release Call for Quality Schools (CQS) application and review process for school partners | RFP/application should solicit a comprehensive plan from partner organizations. At a minimum, plans should address the five levers of the Effective Schools Framework. For districts implementing a two-round CSQ process, this step represents the second round for soliciting final applications to operate partner schools. | CQS / application materials
District approves partner(s) or new schools for school action | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved partner application
Negotiate and approve contract terms and performance expectations for school partners and new school leaders | Negotiations to address: (1) school staffing model, (2) school funding model, (3) initial term length of agreement and renewal conditions, (4) facility agreement; (5) school operating autonomies, (6) performance expectations | Signed partner contracts
Year 1 - Planning Phase 5: Transition - Support transition planning for schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
School calendar and schedule | Partner determines school calendar and schedule | Partner board minutes
District services | District has given partner a list of services that are available for purchase and their respective prices | List of services
Budget autonomy | Partner organization has adopted budget for its schools | Partner board minutes
Partner school funding | Partner organization receives access to contracted funds in the amount and on the cadence agreed to in the contract | Partner organization verification
Staffing autonomy | Partner is able to hire and compensate school staff as it sees fit (in accordance with the contract) | Partner organization verification
Partner-district operating procedures | Partner and district have clear written operating procedures that address high-priority interfaces (e.g., finance, HR, discipline) | Partner organization verification
Year 2 - Implementation: District implements partnership with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School opens operated by partner organization
District and partner have agreed to a data reporting plan and cadence | District and partner organization establish date reporting plan that is aligned to partner contract and ensures timely reporting of leading and lagging indicators. | Data reporting plan
District implements in-district authorizing activities to monitor partner performance (as outlined in contract) | Authorizing activities defined by district authorizing policies and partner contracts; may include, but not be limited to: 1) Annual academic, financial, and organizational review of school performance; 2) Interim data reporting to track leading indicators of school performance; and 3) On-site, third-party school review visits during the first and subsequent years of school opening aligned to Texas Effective Schools Framework (ESF) levers. | Partner and/or district performance reports

## SA-New School, District Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-New School: District Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a new school campus. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Review and update (as necessary) district student enrollment policies for the new school | In addition to new school opening policies, district should consider if any "student enrollment policies" need adoption or revision to implement planned school actions. | - Student enrollment policies - Board meeting minutes for policy revisions/adoption (if applicable)
Year 1 - Planning Phase 3: Recruit - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for recruiting school leaders and/or organizations to plan and open new schools. | Districts should develop a strategic plan for recruiting individuals or organizations to plan and implement the new school. | School leader recruiting summary document
Year 1 - Planning Phase 4: Approve - Approve and finalize plans and performance agreements for new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Leaders participate in a new school design program and develop a plan for the new school | Leaders complete a rigorous new school design program that results in a new school design plan that includes but is not limited to the school's educational program, school culture, operations plan, and systems and structures for improvement. Plans should address the five levers of the Effective Schools Framework. | New school design plan
District superintendent and board approves plans for new school opening | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved new school design plan
Finalize performance expectations and district operating support for new schools. | As part of new school approval process, district should established performance agreement for the new school that establishes performance expectations, including enrollment targets for students that have attended or who are zoned to attend a Comprehensive or Targeted school. The performance agreement should also address plans for operational flexibilities (if applicable) that will be granted to the new school, and how the district will support and manage implementation of the educational model described in the new school's design plan. | School performance agreement
Year 1 - Planning Phase 5: Transition - Support transition planning for new schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
Year 2 - Implementation: District implements new school with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
New school opens
New school meets student enrollment targets | Enrollment at a new school must prioritize students attending or zoned to a 2019–2020 Comprehensive and/or Targeted School. | Student enrollment data
New schools operates with appropriate autonomies | District is providing appropriate operating autonomies to new schools as defined by school performance agreement. | School performance agreement
School participates in formative school quality review process with third party technical assistance provider organization. | District partners with third party technical assistance provider organization to conduct a formative, on-site school review process aligned to the ESF framework. Review process provides formative feedback on school practices and alignment to new school academic model. | School review report

## SA-New School, Partner Managed
After completing the Turnaround Foundations tab, only complete one Turnaround Method tab.
School Action-Restart: Partner Managed Plan
In this section, describe how the selected school action will help the district build systems and capacity so that the campus can achieve and sustain the vision for each Essential Action shared on the Turnaround Foundations tab. You do not have to complete all rows in this section, but all of the six Essential Actions reviewed during the diagnostic must be included.
Describe how you will build systems, skills, and capacity in district and campus staff. | What program or partners will the campus/district work with in this area? | Describe the scope and sequence of training and ongoing coaching efforts, including who receives the training/coaching. | List the Essential Action(s) that this capacity building impacts.
School Action Planning Milestones
In this section, detail the district's plan with start and end dates as well as any additional information to achieve critical planning and implementation milestones that the district will meet in each year in order to plan and execute the school action selected.
Year 1 - Planning Phase 1: Envision - Align school action strategy with district vision for student success
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Develop communication plan for school action implementation | Communication plan should identify specific strategies. For instance, plan should describe planned communication activities that will support board consideration/vote on a district authorizing policy. The communication plan should be a "living" document that is actively updated and modified throughout the grant period. | Strategic Communication Plan
Year 1 - Planning Phase 2: Develop - Develop policies and systems for authorizing school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish organizational capacity/leadership to manage school action implementation | The district organizational management plan should identify what additional resources and district employees will support school action planning, and the reporting structure within the district leadership team. | District project manager and organizational management plan
Adopt district authorizing policies | District must adopt the TEA model authorizing policy if implementing partner-managed school models. In addition to authorizing policies, district should also consider if any "school choice policies" need adoption or revision to implement planned school actions. | District authorizing policy and board minutes
Conduct financial spending analysis in accordance with TEA requirements | LEAs pursuing a partnership-managed model must perform a financial spending analysis in accordance with TEA requirements. The financial spending analysis will provide critical information to inform contract negotiations with partner organizations, including data on current per pupil spending amounts for district schools and the costs of district-provided services to schools. School action providers can share information about technical assistance organizations that can assist districts in conducting this analysis. | Financial spending analysis
District completes required online learning modules or Leadership Academy program from the Texas Authorizer Leadership Academy (TALA) initiative | For districts implementing partner-managed models, the district must commit to participation in the Texas Authorizer Leadership Academy (TALA). TALA is a new, TEA sponsored charter authorizer support initiative to improve district authorizing practices and orient district leaders to replication and expansion strategies. TALA will offer training to school district leaders via competency-based online modules, and annual intensive leadership academy, and an annual summit conference, in addition to an authorizer framework and handbook. At a minimum, districts must complete the TALA online modules or the Leadership Academy. | Completion of TALA online modules or Leadership Academy
Year 1 - Planning Phase 3: Recruit for Call for Quality Schools - Recruit and cultivate education leaders and organizations to implement school actions
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish strategy for building a pipeline of partner organizations and school leaders | Based on selected school action(s), districts should develop a strategic plan for recruiting and/or developing partner organizations and school leaders. | Partner recruiting strategy summary document
Year 1 - Planning Phase 4: Authorize - Finalize plans for partnerships/new schools and execute contracts
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Release Call for Quality Schools (CQS) application and review process for school partners | RFP/application should solicit a comprehensive plan from partner organizations. At a minimum, plans should address the five levers of the Effective Schools Framework. For districts implementing a two-round CSQ process, this step represents the second round for soliciting final applications to operate partner schools. | CQS / application materials
District approves partner(s) or new schools for school action | Likely a two-step process where district superintendent selects/recommends and board approves. | - Board approval meeting minutes - District-approved partner application
Negotiate and approve contract terms and performance expectations for school partners and new school leaders | Negotiations to address: (1) school staffing model, (2) school funding model, (3) initial term length of agreement and renewal conditions, (4) facility agreement; (5) school operating autonomies, (6) performance expectations | Signed partner contracts
Year 1 - Planning Phase 5: Transition - Support transition planning for schools
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
Establish systems and capacity for formative, ESF-aligned school quality review process; including plans for engaging third party technical assistance providers | Districts should establish contract with a third party technical assistance provider organization to conduct a formative on-site school review visits during the first and subsequent years of school opening. School review process should be aligned to ESF framework and focus on quality school practices and alignment to new school academic model. | Progress Monitoring Plan
School calendar and schedule | Partner determines school calendar and schedule | Partner board minutes
District services | District has given partner a list of services that are available for purchase and their respective prices | List of services
Budget autonomy | Partner organization has adopted budget for its schools | Partner board minutes
Partner school funding | Partner organization receives access to contracted funds in the amount and on the cadence agreed to in the contract | Partner organization verification
Staffing autonomy | Partner is able to hire and compensate school staff as it sees fit (in accordance with the contract) | Partner organization verification
Partner-district operating procedures | Partner and district have clear written operating procedures that address high-priority interfaces (e.g., finance, HR, discipline) | Partner organization verification
Year 2 - Implementation: District implements partnership with fidelity
Critical Implementation Milestone | Milestone Description | Acceptable Evidence | Start Date | End Date | Notes
School opens operated by partner organization
District and partner have agreed to a data reporting plan and cadence | District and partner organization establish date reporting plan that is aligned to partner contract and ensures timely reporting of leading and lagging indicators. | Data reporting plan
District implements in-district authorizing activities to monitor partner performance (as outlined in contract) | Authorizing activities defined by district authorizing policies and partner contracts; may include, but not be limited to: 1) Annual academic, financial, and organizational review of school performance; 2) Interim data reporting to track leading indicators of school performance; and 3) On-site, third-party school review visits during the first and subsequent years of school opening aligned to Texas Effective Schools Framework (ESF) levers. | Partner and/or district performance reports