## District Project Planning Tool
TEA INSTRUCTIONAL CONTINUITY PROJECT PLANNING TOOL
Phase | Ref | Planning Category | Description | Activities | District Owner | Suggested Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Phase 0: Project Management Goal: Establish task force, timelines and project plan | 0.1 | Establish Planning and Management Structures | Identify key decision makers, roles and project plan | Outline cross-departmental district task force, expectations, structure, and meeting cadence for instructional continuity planning | Team Lead | bar: Suggested Day 1 to Suggested Day 21
|  |  |  | Create a project plan with activities, owners, and timelines; Districts should adapt the Instructional Continuity Planning Tool spreadsheet to be relevant to local context. | Team Lead | bar: Suggested Day 1 to Suggested Day 21
Phase 1: Conduct Landscape Analysis Goal: Gather data to understand current state of technology, platform and instructional materials access | 1.1 | Assess At-Home Technology Access | Understand student and teacher access to technology - devices, connectivity, software - and identify opportunities to expand access | Survey students and teachers to assess existing student access to technology, including hardware, software, and connectivity. | bar: Suggested Day 1 to Suggested Day 21
Compile, organize, and analyze results from the surveys to determine delivery model limitations. | bar: Suggested Day 1 to Suggested Day 21
Identify low-lift, high-yield opportunities to increase technology access (e.g., hotspot rental program, hardware pickup, etc.) | bar: Suggested Day 1 to Suggested Day 21
Develop local partnerships to increase access to technology. | bar: Suggested Day 1 to Suggested Day 21
| 1.2 | Assess Access to Instructional Delivery Methods | Understand the level of teacher and student access to learning platforms | Create inventory of platform options based on existing licenses and/or free resources | bar: Suggested Day 1 to Suggested Day 21
Assess supports for all learners when considering instructional delivery methods | bar: Suggested Day 1 to Suggested Day 21
| 1.3 | Assess Instructional Materials Access | Identify high-quality and aligned instructional materials | Set instructional continuity vision for all subjects | bar: Suggested Day 1 to Suggested Day 21
Understand access of all previously purchased products | bar: Suggested Day 1 to Suggested Day 21
Explore and analyze additional material options | bar: Suggested Day 1 to Suggested Day 21
Review statewide guidance on course level materials by grade and subject area for consideration | bar: Suggested Day 1 to Suggested Day 21
Assess supports for all learners | bar: Suggested Day 1 to Suggested Day 21
Assess availability of progress monitoring tools across existing options | bar: Suggested Day 1 to Suggested Day 21
Phase 2: Determine At-Home Instructional Model and Monitoring Goal: Make decision on curriculum and instructional Model and policies based on landscape analysis | 2.1 | Determine At-Home Curriculum and Instruction Model | Make decision on at-home curriculum and instruction model based on current state of student and teacher access | Select instructional materials and delivery method by grade, content area and special student populations based on input from landscape analysis | bar: Suggested Day 1 to Suggested Day 21
Test and confirm digital access for all selected materials and delivery methods | bar: Suggested Day 1 to Suggested Day 21
Identify or create scope and sequence by subject and grade level for remainder of school year | bar: Suggested Day 1 to Suggested Day 21
| 2.2 | Set Grading and Progress Monitoring Policies | Set at-home grading and progress monitoring policies for students | Determine grading procedures and policies for monitoring student performance | bar: Suggested Day 1 to Suggested Day 21
Set graduation policies through individual graduation committee reviews | bar: Suggested Day 1 to Suggested Day 21
Determine attendance policies for students in an at-home learning model | bar: Suggested Day 1 to Suggested Day 21
Phase 3: Operationalize the Instructional Model Goal: Solidify plans for instructional model and execute the plan with identified stakeholders. | 3.1 | Design At-Home Learning Schedules | Design daily student schedules to continue student learning | Identify time constraints around existing school day (e.g,. screen time, etc.) | bar: Suggested Day 1 to Suggested Day 21
Set weekly and daily schedules for teachers and students aligned to selected instructional materials | bar: Suggested Day 1 to Suggested Day 21
Develop and incorporate progress monitoring plan by subject area and grade band into weekly schedules | bar: Suggested Day 1 to Suggested Day 21
Create plan to track and monitor attendance | bar: Suggested Day 1 to Suggested Day 21
| 3.2 | Adapt Staffing Models | Adapt district and school staffing models and expectations based on at-home model | Identify staffing needs based on selected curriculum and instruction model | bar: Suggested Day 1 to Suggested Day 21
Update roles and responsibilities of all school and district level positions included in staffing model | bar: Suggested Day 1 to Suggested Day 21
| 3.3 | Communicate Plan to Stakeholders | Design and oversee communications plans for school leaders, teachers, parents and students | Create communiations plan and timeline of key messaging for all stakeholders | bar: Suggested Day 1 to Suggested Day 21
Communicate at-home curriculum and instructional model to teachers | bar: Suggested Day 1 to Suggested Day 21
Communicate at-home curriculum and instructional model to parents | bar: Suggested Day 1 to Suggested Day 21
Provide ongoing communications as decisions are made and new information is available | bar: Suggested Day 1 to Suggested Day 21
| 3.4 | Provide Model-Aligned Professional Development | Provide training to all school leaders, staff, parents and students | Create training plan and timeline by stakeholder group | bar: Suggested Day 1 to Suggested Day 21
Identify training platform and design trainings for all stakeholders | bar: Suggested Day 1 to Suggested Day 21
Execute trainings as decisions are made and information is available | bar: Suggested Day 1 to Suggested Day 21
| 3.5 | Purchase, Print and/or Distribute Instructional Materials (if applicable) | Oversee distribution of necessary materials to students and teachers | Identify list of needed print-based materials based on instructional delivery model | bar: Suggested Day 1 to Suggested Day 21
Create plan for delivery of materials given identified constraints | bar: Suggested Day 1 to Suggested Day 21
Purchase and/or print any materials not already available | bar: Suggested Day 1 to Suggested Day 21
Oversee logistics of materials distribution | bar: Suggested Day 1 to Suggested Day 21
Create inventory and tracking system to ensure students receive materials | bar: Suggested Day 1 to Suggested Day 21
Phase 4: Monitor, Support, and Continuously Improve the Model Goal: Assess academic and operational implementation and iterate based on data and feedback. | 4.1 | Monitor Student Progress | Understand student progress and deliver targeted support | Design process to track student mastery and growth for districts, principals, teachers and students. | bar: Suggested Day 1 to Suggested Day 21
Create structure and schedule student-teacher conferences for student support. | bar: Suggested Day 1 to Suggested Day 21
Execute and track student-teacher conferences. | bar: Suggested Day 1 to Suggested Day 21
| 4.2 | Provide Ongoing Teacher Supports | Understand teacher needs to improve instructional delivery | Design process for school leaders and coaches to check-in with teachers for support | bar: Suggested Day 1 to Suggested Day 21
Develop check-in template, schedule and execute teacher check-ins | bar: Suggested Day 1 to Suggested Day 21
Create professional development plan to provide ongoing support around use of materials and delivery method | bar: Suggested Day 1 to Suggested Day 21
| 4.3 | Troubleshoot Problems | Develop troubleshooting processes and structures | Develop a help-ticket submission process for students and teachers | bar: Suggested Day 1 to Suggested Day 21
Create a district support team to address help desk tickets | bar: Suggested Day 1 to Suggested Day 21
Provide ongoing troubleshooting services to students and teachers | bar: Suggested Day 1 to Suggested Day 21
Create additional trainings and/or communications to reduce repeated student and teacher challenges | bar: Suggested Day 1 to Suggested Day 21
| 4.4 | Support Ongoing Operations | Develop process to gather feedback from and support end users | Develop a process for stakeholders to submit questions or feedback | bar: Suggested Day 1 to Suggested Day 21
Create a district team to address questions and concerns | bar: Suggested Day 1 to Suggested Day 21
Provide ongoing opeprational support to stakeholders | bar: Suggested Day 1 to Suggested Day 21
Create additional trainings and/or communications to enhance at-home model operations | bar: Suggested Day 1 to Suggested Day 21
| 4.5 | Continuously Improve the Instructional Model | Continuously improving instructional model based on new information and barriers to student learning | Develop a process to collect, categorize, and assess barriers to implementation | bar: Suggested Day 1 to Suggested Day 21
Analyze barriers to implementation and adjust execution based on findings | bar: Suggested Day 1 to Suggested Day 21